UNITED NATIONS CHILDREN’S FUND (UNICEF)

CAMBODIA

CAMBODIA

COMMUNICATION-FOR-BEHAVIOURAL IMPACT (COMBI) PLAN FOR TETATUS TOXOID ELIMINATION (TTE) VIA ENHANCED ANTE-NATAL CARE IN CAMBODIA

#### Draft One Year Proposal

October, 2007– September, 2008

Prepared by:

Dr. Everold Hosein (Ph.D.)

###### UNICEF Communication Consultant and Communication Advisor, WHO Mediterranean Center for Vulnerability Reduction, Tunisia/Communicable Diseases Programme, Geneva

in collaboration with UNICEF/Cambodia,  Cambodia Ministry of  Health, National Center for Health Promotion, National Maternal and Child Health Programme and National Immunization Programme

1st Draft: 20th August, 2007

TO THE READER

For A Quick Read

1.	If you wish to look at just a one-page overview of the

suggested Cambodia  TTE via Enhanced Ante-Natal

Care COMBI Programme, please turn to page 30.

For a Bit More

- If you wish just to look at the strategic design and its

rationale without too much detail, then take a look

at pages 5-22, basically Section 3.

For Much More

- And if you want to look at the details of the

communication actions recommended, then please

take a look at pages 23-29; there is a tentative

budget on page 31 -- this should be looked at in

relation to the proposed strategic interventions.

As these are modified, the budget changes.

COMMUNICATION-FOR-BEHAVIOURAL-IMPACT (COMBI) PLAN FOR Tetanus Toxoid Elimination (TTE) via Enhanced Ante-Natal Care  IN CAMBODIA

#### Draft One-Year Proposal (to be extended  based on impact evaluation)

October, 2007– September, 2008

Prepared by:

Dr. Everold Hosein (Ph.D.)

###### UNICEF Communication Consultant and Communication Advisor, WHO Mediterranean Center for Vulnerability Reduction, Tunisia/Communicable Diseases Programme, Geneva

in collaboration with UNICEF/Cambodia,  Cambodia Ministry of  Health, National Center for Health Promotion, National Maternal and Child Health Programme and National Immunization Programme

1st Draft: 13th  August, 2007

Introductory Notes

# Plan Developed in Consultation

This  COMBI Plan/Strategy for  Tetanus Toxoid Elimination (TTE) via Enhanced Pre-Natal Care  in Cambodia was commissioned by UNICEF/Cambodia as part of a specially-funded programme to eliminate TT infection and neonatal tetanus in Cambodia. The COMBI Plan was developed in the course of a 19-day field mission to Cambodia June 3-21, 2007. It is based on consultations with various levels of staff of the Cambodia Ministry of Health (MOH): National Center for Health Promotion (NCHP), National Maternal and Child Health Centre (NMCHC), National Nutrition Programme (NNP) and the National Immunisation Programme (NIP). A one week field visit to Mondul Kiri and Prey Veng Provinces  provided opportunities to meet with staff at various health centres, several health volunteers in various villages, traditional birth attendants, and mothers of newborns and children under two years of age. A one week COMBI workshop was held for about 35 participants from the different programmes of  MOH (mentioned above) and various other NGO partners working on maternal and child health. Four  working groups presented at the end of the week draft COMBI strategies for dealing with Infant and Young Child Feeding Practices (IYCF), breast feeding, clean and safe delivery, and hand washing. Ideas presented in those reports also informed the design of this COMBI Plan.  Meetings were also held with UNFPA and WHO. A full list of people met and the programme of visits are available from UNICEF/Cambodia Office (Contact: Dr. Viorica Berdaga). Following the Cambodia mission, on-going consultations via e-mail with UNICEF and the NCHP also served to shape the COMBI Plan.

Various background documents were reviewed as part of the planning exercise. These included: 2005 Cambodia Demographic and Health Survey (2005 CDHS);The Cambodia Baby Friendly Community Initiative Strategy by Michelle Lang and Robert Johnston (April 2005); The Development Study on Strengthening MCH Service Performance in the Kingdom of Cambodia- Draft Interim Report, December 2006 by JICA; scripts of BBC World Service Trust TV spots for breast feeding and complementary feeding; Maternal and Neonatal Tetanus Elimination by 2005: Strategies for Achieving and Maintaining Elimination by UNICEF/WHO/UNFPA (November 2000); Obstacles to deliveries by Trained Health Providers to Cambodian Rural Women by UNFPA and the Ministry of Health /Health Sector Support Project, February 2006; MOH National Policy on Infant and Young Child Feeding Practices, January 2002; MOH Five Year Strategic Plan- National Immunization Programme Cambodia 2006-2010; National Nutrition Program (NNP) Annual Operational Plan 2007; Cambodia Child Survival Strategy, MOH (December 2006); Report of Twelve Key Family Practices for Health Baseline Survey Report 2006, NCHP/Cambodia; Comprehensive Midwifery Review- Draft Final Report, MOH/Cambodia, by D. Sheratt, P. White and C. Chhuong; National Communication Strategy for the Promotion of IYCF in Cambodia March 2005-December 2007 by Linkages/Academy for Educational Development and various Power Point presentations on the details of this strategy; UNICEF Internal Case Study on Community Based Approaches to Improve Breastfeeding in Cambodia; UNICEF/Cambodia BRIEFING NOTE: Baby Friendly Community Initiative (BFCI);Maternal and Child Health Knowledge-Attitudes-Practices Survey- Cambodia Endline  Results, September 2006; various government decrees and documents Marketing of Products for Infant and Young Child Feeding; a Child Survival Booklet; Review of Field Based  Child Health  Nutrition Programmes by Ann Canavan (Consultant) & MOH Nutrition Technical Working Group 
Funded by: BASICS II and Helen Keller International); Draft Baby Friendly Initiative Concept Paper –UNICEF;

This draft is to be seen as the first of three rounds of developing a COMBI Plan, in the design approach taken by WHO. This first draft is just that: a first draft. It should be widely shared among colleagues in the various relevant MOH department/programmes/centres involved in the subject matter. A second draft should emerge which takes into consideration the various responses from those who have reviewed the document. We then suggest a meeting hosted by the MOH and  UNICEF and other interested parties at which further discussion of the second draft takes place, and a detailed work plan is finalised indicating who will do what when. The third version to emerge is the “final” document but which itself remains subject to change depending on new circumstances.

# Presumed Context

This plan is presented in a context which presumes that the reader is familiar with the health situation of Cambodia and the nature of the current national  programmes in maternal and child health, nutrition, and immunisation , as reflected in the various documents mentioned above. The DHS 2005 provides an excellent overview of the health situation and serves as a primary source of information on Cambodia. This basic information will not here be repeated except to mention the following:

Cambodia has a population of about 14 million people with about 85% living in rural communities. It is administered via 24 provincial entities. There are an estimated 13,505 villages (1,312 urban, 12,193 rural) and about 2,174, 305 households; this is about 161 households per village.

There are approximately 400,000 births per year. About 70% of newborns seem protected against neonatal tetanus, according to the DHS 2005, with about 54% of pregnant women receiving the two TT vaccinations during their pregnancy.

About 70% of pregnant women nationally receive some minimal level of ante-natal care (ANC). But the timing of this varies especially across the urban/rural landscape. Overall about  23% of pregnant women go for their first ANC visit within the first trimester. Another 26% go within 4-5 months of being pregnant. There is also about a 23% who wait till their 6th/7th/8th month of pregnancy for their first AN visit; and then there is a large proportion of 28% who never get ANC (in some cases because it is not available).

Other relevant information will be provided along the way as we proceed with the COMBI Plan design.

## THE  TTE (via ANTE-NATAL CARE) COMBI PLAN FOR CAMBODIA (2007/2008)

1. Overall Goal

To improve child survival rates in Cambodia by eliminating neonatal tetanus Toxoid infection by ensuring that at least 85% of pregnant women are neonatal  tetanus protected (NTP).

2. Behavioural Objective:

To have 95% of all women who have missed their menstruation/period visit the nearest Health Centre and meet with a doctor/nurse/midwife, within four weeks of missing their period to receive a “package” of health care services (to be defined later and which will include TT vaccination or other assurance of NTP based on previous vaccinations, plus iron follate supplementation, nutrition advice and  birth preparedness tips, ), on the presumption that they might be pregnant or on the confirmation by physical (manual palpation of the uterus) examination that they are pregnant, and in this way have at least 85% of all  pregnant women (340,000 ) receive NTP, among other MCH benefits.

Commentary: This section will explain why this behavioural objective was selected. The essential first step in designing a COMBI (Communication for Behavioural Impact) Programme for TTE via Ante Natal Care is determining the behavioural result(s) desired. A COMBI mantra informs this step:

Do nothing…..make no T-shirts, no posters, no pamphlets, no videos….do

nothing, until there is a clear sharp sense of  intended behavioural outcomes.

This fundamental COMBI planning principle requires us to first define specific and precise behavioural objectives, linked to some overall long-term goal. In the case of TTE, the long-term goal of TTE is directly linked to the child survival outcome of reducing deaths to neonatal tetanus. According to the DHS 2005,  Cambodia is not doing too badly when it comes to protecting pregnant women from neonatal tetanus. The 2005 survey indicates that about 70% of pregnant women were protected from neonatal tetanus (either by being appropriately vaccinated before or during the pregnancy. While this is an impressive level of neonatal tetanus protection, it is still below the target of the 85% (or higher) protection rate desired for TTE. As with so many other health interventions, getting the last few percentage points of success in any health effort tends to be extremely challenging compared to the earlier gains.

The success to date has been due to the keen efforts of the National Immunisation Programme (with its annual campaigns and vigorous outreach activities) in collaboration with the work of antenatal care staff at government health centres as part of the on-going work of the National Center for Maternal-Child Health. But there are emerging constraints (financial and human resources) in the work of both facilities which would add to the challenge of getting the remaining 15%-20% of pregnant women to be neonatal tetanus protected.

To get the final 15%-20%, one approach would be to intensify the annual immunisation campaigns and the outreach activities village by village, household by household. But it seems there are major financial and human resources constraints which would make further intensification not feasible. We therefore ned to seek another avenue for arriving at the final results of a 85% +  NTP rate.

In reviewing the overall situation, it seems that the most strategic approach to ensuring higher levels of neonatal tetanus protection (NTP) is to ensure that all pregnant women visit a government health centre for antenatal care early in their pregnancy to allow for the minimum  two TT vaccinations which would be received during early antenatal care or have confirmed that the pregnant woman is NTP via previous vaccinations (up to 5 before pregnancy). The behavioural objective of the proposed COMBI Plan will therefore focus on getting nearly all pregnant woman to receive early antenatal care within which NTP will be one of the priority items to be addressed, and in this way achieve the 85% and higher NTP.

The dilemma is, however, what to recommend as “early”. Health centres are not yet equipped with pregnancy testing facilities;  so coming in within, say, a month of missing one’s menstruation (period) to determine biochemically whether one might be pregnant is not a selling point. However, a pregnancy can be diagnosed at 7-8 weeks by manual palpation of uterus. So this could be a selling point  for coming in within a month of missing one’s period. And even if one turns out to be not pregnant, there are health services to be offered in that first month or two months of  presumed pregnancy (such as follate acid, iron tablets, TT vaccination, etc) which would not be nullified or be dangerous if one turns out not to be pregnant. One would argue that it is far better to receive these health interventions even if no pregnancy is confirmed later.

We could suggest coming in for that first early ANC visit anytime within the first trimester or even after missing 4 menstruations (periods).  The problem is that if it is in the third month or later of the pregnancy one could not begin the folic acid component of the iron follate health intervention which needs to be started within the first two months of the pregnancy for the iron follate/folic acid component  benefit to have effect. (Verify)  But if we were able to get 85% and higher of the proportion of pregnant women coming for their first antenatal care visit even at 5 months of pregnancy, we could ensure NTP for all of them. So one behavioural approach is to press for coming in for the first ANC visit within a month of missing one’s period, and accept the fact that people will delay and delay and delay but eventually we would arrive at 85% or more coming in at least at the early part of the second trimester, thus ensuring NTP for the targeted level.

Of course, there are so many subsidiary health benefits for the mother and child if ANC could begin much earlier. As a consequence, while the COMBI Plan is technically dedicated at TTE/NTP, the strategic behavioural approach is to encourage the start of ANC within a month of missing one’s period, leading to other MCH benefits in addition to ensuring NTP.

Already about 70% of pregnant women nationally receive some minimal level of ANC. But the timing of this varies especially across the urban/rural landscape. Overall about  23% of pregnant women go for their first ANC visit within the first trimester. Another 26% go within 4-5 months of being pregnant. Our behavioural challenge is to dramatically increase the figure for first trimester ANC first visits and to aim for more of these visits in the early part of the first trimester (within a month of missing one’s period), drawing on the roughly 50% who do go for their first visit within the first 5 months of their pregnancy. These are pregnant women who are already going for ANC; they need to be prompted to walk-in a bit earlier.

There is also about a 23% who wait till their 6th/7th/8th month of pregnancy; they need to be prompted to come on in much, much earlier. And then there is the enormous challenge of prompting a large section of the 28% who never get ANC (in some cases because it is not available) to come on in for the first ANC visit within a month of missing their menstruation.  By intensely focusing on this behavioural objective, we are more likely to get at an 85% first ANC visit within the first 5 months of pregnancy which would allow for ensuring NTP, but also enhance MCH health benefits for the pregnant woman and expected baby.

The emphasis on the first ANC visit being done very early allows for health staff to build a strong bond with the pregnant woman over time, especially if that first visit is welcoming and warm and assuring. It is this first visit which sets up the foundation for subsequent visits. And it is this first visit which would have key implications of increasing the proportion of women who deliver with “skilled attendants” at hand.

By focusing on the above mentioned behavioural objective related to the first ANC visit, in addition to reaching the target of 85% NTP, we are likely to make a substantial subsidiary contribution to reducing maternal mortality in Cambodia (although that is not the primary aim of this COMBI Plan.)

It is of interest, however, to look at these other ANC benefits as side contributions. According to the 2005 DHS, 63% of pregnant women took iron tablets; and about 60% were informed of signs of pregnancy complications. Increasing these levels to over 85% would be a useful contribution to maternal health. About 22% of deliveries take place at health facilities; if we can build a strong bond between the pregnant woman and the midwife at that first ANC visit and continue it in subsequent visits, we can contribute to an increase the proportion of people who deliver at health facilities.

It would not be advisable in a public communication campaign to attempt to address all the above behavioural outcomes hinted at in the last paragraph. The public and  pregnant women will simply be overwhelmed and confused. One needs to limit the behavioural focus if behavioural impact is desired.

It seems that the foundation for improved NTP and maternal health and child survivability rests with that first ANC visit, and the earlier the better. One quickly realizes that all the subsequent “maternal health” behaviours hinge on this fundamental first behaviour:  visiting the midwife or other health staff at a health centre within a month of missing one’s period.

To repeat: If this can happen, and if that first visit goes well, then all the subsequent behaviours are more likely to follow with appropriate nudges and guidance: ensuring NTP, taking iron follate supplements, better nutrition, making the follow-up ANC visits, and being advised on what action to take in response to the danger signs. While there is no 100% guarantee that the first behaviour will lead ultimately to the others, there is the greater likelihood of success with the other behaviours if this first fundamental behaviour is effectively achieved. The private sector has had renowned success with having the first visit to a shop or center being so appreciated that it serves as the most solid foundation for return visits.

3. Strategy

A general overview of the COMBI Strategy is presented in this section with various interventions typed in “bold” font to provide a sense of the mix of interventions. Further specification of the communication actions suggested will follow in the subsequent section and a short summary of the interventions will be presented at the end of Section 4.

  - The COMBI strategy here proposed is behaviourally driven: it focuses on that ultimate result of 95% possibly pregnant women visiting a health centre and meeting with a midwife or other appropriate health staff within four weeks of having missed their period. At this visit, the women will obtain a package of ANC health services including NTP. (The exact components of the “package” beyond NTP is to be decided in consultation with the NMCHP.)The strategy presented below is based on some understanding of those factors which would hinder this behaviour and those factors which would facilitate it.

  - The COMBI strategy for the above behaviour needs to be informed by the available data and other insights as to why people would carry out the recommended behaviour, or not.

  - A review of field observations and conversations in Cambodia suggests that individuals will follow-through with the recommended behaviour if in their cost vs. value calculation they conclude that it is worth it to invest the effort and bear the “cost” in carrying out the behaviour in relation to the value of what they receive in return, and in relation to what other “competition” there is in the environment or “market place.”

  - For many people, they see no value in the very early first visit for ANC. The fact that they have missed a period is no big deal; it is just a temporary internal imbalance, they believe. And so they will wait, and wait, and wait.

  - Many are not aware of any particular advantages to visiting a midwife within the first trimester, much less four weeks after missing one’s period. No one has provided them with information regarding the value of the  very early first ANC visit. In many instances, people are not aware of the value of folic acid or iron follate supplements, or  have even heard of it, or know that the folic acid contribution of iron follate tablets is more effective when taken within the first 8 weeks of pregnancy (Verify).  On the other hand, the extensive outreach immunisation activities have clearly prompted the value of TT vaccination.

  - Then there are instances, where people know the advantages but do not think the advantages are worth the effort to come in very early. They believe they can have the “value” of an early visit also at a late visit. In their minds, coming in within 4 weeks of missing one’s period is no different than coming at 13 weeks or 15 weeks; the midwife will do the same things on both occasions. Their view is that whatever services they can get in the first four weeks after missing their period, they can get later in the first trimester or even in the second trimester, and so they see no urgency to come in as early as is being recommended.

  - The pressures of other daily demands and the competitor of personal inertia or lethargy prevent one from taking immediate action even when one knows what the right thing to do is. It would seem that people need to be reminded of the value of an early visit to the health centre and be constantly triggered into action as a counter to lethargy.

  - There is social inhibition about disclosing pregnancy. It is as if people would simply notice the pregnancy and one does not have to speak about it.  In the first trimester of pregnancy, there are no outward signs of pregnancy and so to go and find out whether one is pregnant seems unwarranted and would mean that one would then have to disclose openly one’s pregnancy status.

  - There is fear of needles. And if one anticipates a tetanus shot as part of that first ANC visit, there would be some trepidation about rushing in early for something which has a measure of discomfort.

  - In the case of having to start iron follate  tablets as part of the first ANC visit, others have shared the “side effects” of taking iron follate supplements.  So one is a bit hesitant of having to put up with these side effects earlier than necessary.

  - There is the time and effort involved in going to the health centre with no clear assurance that a midwife or appropriate health staff will be present. There is the travel distance between home and the health facility. There is the cost (money) for that first ANC visit. There is the re-scheduling of home tasks in order to have the time to make that first ANC visit. Transportation costs and opportunity costs, and time and effort, all add up in relation to what is gained from an early visit. We will need to engage possibly pregnant women in looking at the value side of the costs vs. value calculation. This is discussed later.

  - On the other hand, at least 50% of pregnant women see the value  of coming for at least one ANC visit within the first six months of pregnancy, and about half of those within the first trimester.  This proportion is closer to the behavioural objective in that they already come, and now the motivational engagement would focus on having them come in earlier.  There is another portion who come in within the last trimester; they will need an extra motivational engagement to prompt a much earlier first ANC visit.

  - And then we have the more challenging group of about 30% who never receive any ANC care. The motivational engagement here is going to be quite substantial as it will need to explore the reasons for no ANC visit. One simple explanation is that for a certain proportion of this group, ANC services are simply not available. We do not know exactly what proportion has no access to ANC services.  We will need to focus on that portion for whom ANC services are available but for whom there seems no special value in obtaining these services.

  - We eventually need to arrive at a set of “Communication Objectives” which, if achieved, will get us the behavioural result. These communication objectives would set out the costs vs value relationship of carrying out the recommended behaviour and offer the key messages one would need to engage possibly pregnant women to consider and deliberate over.

  - The costs vs value calculation for the recommended behaviour will need to be carefully attended to in the communication strategy. (All behaviour is chosen following an individual’s calculation of the cost vs value and the conclusion that the costs seem in harmony with promised value.)  One would have to present the health care package offered at the first early ANC visit as being wonderful even if it turns that one is not pregnant. But  if it turns out one is pregnant, then the early start on these health measures (as part of the package) would provide an early start for a lovely healthy baby and a mother who will be around to care for that spectacular, miraculous child.

  - The messages need to address both the Head (logic) and Heart (emotional) dimension of the Cost vs Value calculation. On the value side, we would need to point out that if you want to ensure against malformed babies, then folic acid taken early in pregnancy  as part of the iron follate tablets will prevent malformation, but that this needs to be taken early within those first 8-12 weeks. (Verify)  And there are other value items to be added: learning about better nutrition; taking the various blood tests early and dealing with any consequential action; learning to be watchful for danger signs and acting on them; being able to have the recommended 5 other antenatal visits to ensure a safe birth and healthy baby.

  - In addition, we need to think of a modest incentive (a small gift of cosmetics or a T-shirt, etc) to be promised (as part of the communication effort and the ANC health care package) to every woman who comes in as recommended. A modest incentive offers a way of reducing cost burden and also giving a little extra value to the recommended behaviour. The recommended behaviour will also need to be branded; branding also adds perceived value to a behaviour or product.

  - The messages will need to address in simple language the value of such things as iron follate tablets, TT vaccination and NTP, and the critical time element to these, especially the first for the folic acid component contribution of iron follate tablets, plus an early start on birth preparedness and watching out for pregnancy danger signs. Women will act on the recommended behaviour if they are properly engaged in looking at the costs vs value relationship of carrying out the recommended behaviour in relation to the outcome of a healthy, lovely  child who will survive and a mother who will also survive to provided loving care. And, to repeat,  we will need to address the cost vs value calculation in relation to what alternatives or competitors there are. As they say in the business world, you do not know what something really cost until you have seen the alternative, even if the alternative is to “Do Nothing”.

  - The discussion above  offer the broad outline of what we can offer individuals in terms of the value of the recommended behaviour in relation to the “cost” involved in carrying it out and in comparison to doing nothing or just waiting for later. In this outline are the themes which will form the basis for engaged communication with a wide variety of people in Cambodia, both male and female, but with the ultimate focus being on the behaviour of the possibly pregnant woman.

  - A woman who has missed her period will carry out the recommended behaviour (based on some assumptions as to what will be in “package of services” received at the first antenatal visit within 4 weeks of missing one’s period)  if she is:

    - Persuaded that getting folic acid as part of iron follate supplement early (i.e. within  --- (#)  weeks of being pregnant) will ensure that the baby has no malformations; and that at that first ANC visit as recommended, folic acid will be given as part of the iron follate tablets to be provided.

(Verify)

    - Convinced that getting adequate  TT vaccinations prior to delivery will ensure that her baby will not get a tetanus infection (e.g.from unclean cutting of the umbilical cord or unhygienic care of the cord) and possible die as a result; and that at that first ANC visit as recommended NTP will be assured and TT vaccination sgiven as needed.

    - Persuaded that starting early on iron follate supplementation will decrease anemia in her, give her more energy, and ensure a safer baby delivery; and that at that first ANC visit as recommended iron supplementation will begin.

    - Assured that specifically mentioned side-effects of iron follate supplementation (changes in the stool, etc)  are minor and is worth the costs/burden in relation to the tremendous value/benefits gained.

    - Convinced that better nutrition for herself as a pregnant woman will make for a stronger and healthier baby and enable her to carry the pregnancy with greater ease and comfort and energy; and that at the early ANC visit recommended she will be given advice on hot to start very early in her pregnancy on improved nutrition for herself an her baby.

    - Assured that the earlier she starts planning for the birth of child the better things will be and that part of the planning is to look out for danger signs and to act promptly on them.

    - Assured that when she makes that early first ANC visit as recommended she will receive a special gift for coming in.

    - Reminded wherever she turns that the branded recommended behaviour is the thing to do if she has just missed her period.

    - Reminded that health centre staff are trained and qualified and available and ready to welcome her with open arms and offer her the best care possible.

    - Reminded that what she really wants is to deliver a lovely, beautiful, healthy child and to be alive to hold, caress, love and care for her baby; that it does take some time and effort and money to make that early visit; but in the end, it is worth when one holds with overwhelming joy and love the miraculous baby in one’s arms right after birth.

  - As we have mentioned, the above 10 communication themes are all part of the cost vs. value calculation which individuals carry out in deciding on behavioural options. Sometimes the calculation is not all logical; often emotions play a critical role; and human behaviour in any case remains a daunting mystery – we do the oddest things for strange reasons.

  - While the above-mentioned themes of the cost vs. value calculation will form the content of the “conversations” we need to have with the people of Cambodia as they consider the recommended early ANC visit behaviour ,a favourable cost vs. value calculation, while necessary, is often not sufficient to prompt the desired behavioural response. People may know the right thing to do but still don’t carry it out. People need to be triggered and nudged and encouraged to do what they already have calculated is the “right” thing to do. And some of these triggers can be provided by other family members,  neighbours, friends, relatives, religious leaders, co-workers, and other community members. Here too lies the value of modest incentives and branding of the recommended behaviour.

  - Pre-Requisite: There is a prerequisite which needs to be stated upfront. Before this COMBI Plan is implemented, there should be full assurance from the NMCH Programme that all 1000 (roughly) health centres throughout Cambodia (or most of them) are in a position to offer a basic package of health services as part of the first ANC visit within the first trimester of a pregnancy, and especially within the first 4 weeks of a woman having missed her period; the “package” will include iron follate tablets, NTP,  nutritional advice, and birth preparedness tips/pregnancy danger signs guidelines and immediate actions to be taken.

  - Further research: There are some indications that people are reluctant to visit government health facilities unless it is necessary. One is not sure about the basis for this judgment and action. But it might be useful to have some qualitative study of this reluctance if it exists and to determine what factors serve to inhibit people from visiting the health facilities. If it is a matter of the attitude of health care providers which results in poor interpersonal relations, or unavailability or erratic availability of services, then these may need to be addressed prior to launch of a COMBI Programme. In addition, it would be useful to have some in-depth interviews with women who may know the value of early ANC care but do not receive any ANC care at all, to explore why no ante natal care. Similar further research would be useful regarding the reasons which may explain the behavioural rationale for those who come in for their first antenatal care visit in the last trimester. (If time does not permit for this sort of further research to be done, then we should proceed on the basis of current insights.)

  - The proposed COMBI Plan focuses on the specific desired behavioural result indicated earlier and consists of an integrated, judicious mix of a variety of communication interventions responsive to the issues raised above.

  - One of the early actions required will be to brand the recommended behaviour: If you have missed your period, then within 4 weeks go to your health centre for your first “antenatal care” visit. The branding should consist of both a special logo and tag line/phrase. A graphic design firm or advertising agency should be selected to develop this logo/theme through a competition with a fixed monetary prize going to the winner.

    - In English, one possible branding approach could be the following:

Missed Your Period?

<4W

Within 4 Weeks, come visit your health centre

You may be pregnant. Start early to care for and love that baby. And start preparing to be a caring. loving mother.

The earlier the better.

Perhaps some similar design in Khmer  could be done. The <4W symbol  suggest  “in less than/under 4 Weeks”.

    - Cambodia has had a National Maternal and Child Health programme for many years now. And most people seem to know about the recommendation to get some kind antenatal care prior to delivery; about three-quarters do in fact get some kind of antenatal. We suspect, however, that the NMCH “brand” has gotten a bit jaded as many government programmes and commercial products do. And so too the general advice of receiving antenatal care. But because of this familiarity, people may more easily dismiss any new messages unless they stand out distinctively.  As in the private sector, sometimes one needs to take an old brand of a product, make a some modest changes to the product (for example, with say Colgate toothpaste,  add a teeth whitener chemical, give it a new “pumped-up” name (such as Colgate Plus--Colgate +) and launch an effort which says we have something even better than the last time with the additional benefit of the teeth whitener. This sort of re-branding is now quite common in WHO and UNICEF where we have found new terms and logos to address old health issues such as malaria, TB, maternal and child health, etc. We need to do something similar to this behavioural recommendation of early antenatal care under the NMCH umbrella.

    - The behavioural theme/logo should be simple and elegant in design, easy to duplicate and in two colours. The logo need not have any symbolic meaning in relation to antenatal care; by constant use it will be become associated with  the recommended behaviour, in the same way the “swoosh” of Nike which has nothing to do with athletic shoes has become associated with that brand of product over the years. Eventually one may wish to just use the logo by itself as a trigger for the recommended behaviour All communication materials, letterheads, folder etc, associated with this COMBI Plan should carry the logo and colours, even when associated with existing logos for the NMCH, or NCHP, or the National Immunisation Programme. The above <4W logo is merely suggested at this point but will be used henceforth in this document until an approved alternative is agreed upon.

.

  - The key behavioural theme will then need to be put into some simple form to be used in all media and communication actions. The following is one such attempt and will need to be expressed in appropriate Khmer: “An important public message for Cambodian women – If you have missed your period (alternatives: menses? menstruation?),please come in within four weeks of missing your period and see a midwife at your local health centre. You may be pregnant. Start early to care for and love that baby. And start preparing to be a caring, loving mother. Look for the <4W sign and come on in.  We would be happy to see you. And remember: the earlier you start  the better for you and your baby.

  - We then go on to add in an extended version, and in intimate, effective Khmer-language:

    - “…………You might very well be pregnant. And the earlier you find out, so much the better. There are three things we can offer you immediately which will make for a healthy pregnancy, safe delivery and a wonderful baby: (1) You start with iron follate tablets early so that the folic acid part of these tablets can begin their work to prevent malformations of the baby.. This must be done in the first 12 (?) weeks of pregnancy to have the best effect. Later will not work for the folic acid part of the iron follate tablets. And in Cambodia there is still a chance of malformation. So come in and get your iron follate tablets early. The iron part of the iron follate tablets prevents anemia [Note: Anemia may need to be further explained…], and you know that most women in Cambodia are anemic and this can lead to very serious complications in delivery if not taken care of; plus taking the iron follate tablets gives you more energy during your pregnancy; (2) We will make sure that you and your baby are protected from tetanus toxiod infections. Many babies in Cambodia still die soon after birth because of tetanus, usually caused by unclean cutting of the umbilical cord and  unclean care of the cord. We will make sure you have the right number of tetanus shots so that you and your baby are protected from tetanus infections. (3)  We’ll give you a very nice Pregnancy Welcome Kit with a special gift (Note: To be described later) when you come in to see your midwife within 4 weeks after your have missed your period. And in the Kit we’ll have  your Mother and Child Loving Care (MCLC) Card  (Note: to be described later) with clear instructions on what to do if any of 12 danger signs should occur which may threaten your pregnancy or even your life and that of the baby.  And also in the Kit will be advice about good nutrition for you while you are pregnant. This would help you and your baby …………

  - The above is suggestive of what can be said but basically we want to suggest the recommended behaviour and explain why in terms of “cost” vs. value it is worth carrying out the behaviour.  It is an attempt to cover the key points  in 3.20 above. Please note that this is a first attempt at such compression of key points and will benefit form further review and revisions.

  - The heart of the COMBI Strategy is what the private sector would call direct sale or personal selling: the door-to-door, face-to-face  engagement of the consumer in his or her home. The mass media will also be used and will provide the backdrop for the more personal engagement which takes place between a “personal seller” and a woman. It is widely recognised that the ultimate key to action on a recommended behaviour is in the personal interactions between the consumer and a “seller”. It is the personal communication between a woman who may be possibly pregnant and a “TTE/NTP/ANC” personal seller  (to be called by a different name as suggested below)which will be the primary means for prompting that early ANC visit and for making that first visit a memorable lovely visit. The COMBI Plan will use the concept of personal sellers in two ways: one has to do with door-to-door communication between a volunteer/Ambassador and a family of each home in Cambodia with regard to the behavioural theme, and the other has to do with personal care as conducted by midwives at each health centre.

    - Firstly, by a newly-branded core of some 13,500  volunteers to be called Mother and Child Loving Care Ambassadors (MCLCA), each of whom will be asked in the first two months of the COMBI programme  to visit  four homes per day/evening in their neighbourhood/village ( for a total of 2,200,000 homes covering all of Cambodia)  for a quick 15-minute home visit, and to repeat this quick home visit to the same homes six months later. Other than these home visits specifically intended for promoting the <4W  behaviour, the MCLCA will available in the village for helping a possibly pregnant woman who has missed her period to get to a health centre for her first ANC visit within 4 weeks of missing her period.  Each MCLCA will be assigned a specific area and specific households in that area. At each home, the MCLCA will hand out a single-page, two-sided  “<4W  Advisory Sheet” (described later), which covers the behavioural theme expressed above, in a nicely laid out presentation. On one side is the basic behavioural message and rationale, with the key behavioural theme mentioned at least three times.  On the other side would be a game/quiz of 10 multiple-choice questions with some answers being humorous which a family member can try to answer. The correct answers will be at the bottom of the page upside down. Each household should get at least one of these sheets, even if there is no one of fertile age in the home. Grandmothers and older women can be useful, credible sources of information for others. The MCLCAs will go over the basic behavioural theme of the sheet as she hands over the sheet and tries to emphasise the key behaviour recommended at least three times in the sheet. The Ambassadors will focus on the recommendation of going to a health centre for that first ANC visit within 4 weeks of missing one’s period. They will pay special attention to the cost/value decision-making process.  And they will point out the small special incentive the possibly pregnant woman will receive when they go to the health centre for that first ANC visit; the incentive will as part of a Pregnancy Welcome Kit given out at the health centre. The MCLCA will also stress that if any of the women should miss their period, they should immediately contact their Ambassador who will help them get to the health centre for that first ANC visit within four weeks of missing a period. She then urges family members (wives, husbands, in-laws) to try the quiz at the back page. The MCLCA also asks if they have any questions and sensitively responds to these questions.

    - As soon as an MCLCA is contacted by a woman who has missed her period, she should undertake a second home visit and engage the woman in arranging to make that early first ANC visit within four weeks. The MCLCA should be ready to review any of the issues which may come up as part of the woman’s cost vs. value calculation regarding the recommended behaviour. The MCLCA should ensure that on the first visit the woman gets NTP ( to be indicated by a special Gold NTP Star to be stuck on the Pregnancy Welcome Kit –described later.)

    - These Ambassadors will continue to be a counselling source to each woman who turns out to be pregnant. On average  there will be one MCLCA per every 30 or so pregnant women, depending on household distribution per province. This converts to about  2-3 pregnant women/mothers per month; less than one per week on average. In addition to prompting the <4W  behaviour, the MCLCAs will be available for other mother-child “loving care” work. For example, they can continue to offer advice to the woman on taking the iron follate  tablets and dealing with side-effects. They can also offer advice on nutrition and help the woman watch out for danger signs. They can also facilitate and ensure delivery with the midwife or other skilled attendant present. Later on they could be asked to counsel the woman on exclusive breastfeeding and may be asked also to  focus on infant and young child feeding (IYCF) practices. These would all be a continuation of “Loving Care”.

    - The MCLCAs are not intended to be a new group of people/volunteers recruited. There is already a significant network of health volunteers at the village level which the MOH has spent several years building. The Community Based Baby Friendly Initiative  has also used volunteers such as Model Mothers.  In some places, these volunteers work very well and in other places not so well. Their role as volunteers has also become jaded in many communities. Some of them are quite tired. Some do very little community outreach. The MCLCAs should be drawn from the current crop of volunteers in existence but using  a new criteria of selecting people who are already employed (so receiving income for this community mission does not become an issue) and people who have indicated by their output a measure of commitment to community action. It is suggested that one member of the existing Village Health Volunteer Team be selected/designated  as the MCLCA for that village. Where the Village Health Volunteer Team does not exist, the local health centre staff should select in consultation with village leaders one individual to serve as the MCLCA.  In the main the MCLCAs are likely to be women but men should not be automatically excluded. And some of them may be drawn from among traditional birth attendants but who will agree to serving exclusively as MCLCA Ambassadors and ensure that every birth is attended by a mid-wife.  While current health volunteers cover a variety of health topics, the MCLCAs (when wearing the MCLCA “uniform”) will focus exclusively on mother and child loving care behaviours. On other occasions they may wear another “uniform” and focus on other health behaviours.   This is basically a re-branding of existing volunteers and traditional birth attendants. The re-branding gives them a bit more status, embellishes their presence in the community, raises their profile, and presents a fresh face of some old health themes.  Even the term “Loving Care” brings in a non-medical/non-health dimension which taps into existing needs/wants/desires. MCLCAs will be encouraged to go beyond health rationales and invoke the theme of “loving care”.

    - Each MCLCA will be given a large <4W badge and special coloured light-cotton jacket/vest to wear on their home visits. Each MCLCA should receive a personally addressed memo from the most senior MOH official (if not the Minister himself) requesting their keen participation in the home visit programme and thanking them for their past effort to provide excellent maternal and child health care.

    - Each MCLCA in groups of 20-25 will receive two-day non-residential training  by their local midwife who will serve as their Mentor/Trainer and informal supervisor. The training should cover the key elements of the <4W Information Sheet; one day should be spent on all the technical information they need to be aware of; and the second spent in role playing sessions in which each  MCLCA plays the role of  a household member and each plays the role of Ambassador going through the process of engaging the wives and husbands and in-laws in the  discussion of the <4W behaviour.

    - The MCLCAs will not be paid but they will be rewarded in various ways  and provided with on-going motivational social opportunities for sharing experiences.  Three quarterly gatherings of the MCLCAs  (in groups of  50) will be held at various provincial locations. At these gatherings they will be thanked by the most senior MOH officer available at that level, provided with a simple meal (tea and cakes?)  and given gifts donated by the private sector through a Business Partnership for Mother and Child Loving Care to be established. These gifts might include packages of non-perishable foodstuff.  They will also have an opportunity to share their experiences with their colleagues. In the last quarter of the first year, a provincial Thank You Ceremony will be held for all MCLCAs and midwives from each province at which a simple meal will be served, a Certificate of Appreciation signed by the  Prime Minister or Minister of Health handed to each, private sector-secured gifts given to each, and a Lucky Draw Prize given to one lucky MCLCA and his/her Mentor Midwife from each province. The Prize could be an all expenses-paid three-day weekend trip to Bangkok or a Cambodia beach resort donated by a hotel and airline company. The certificates and  thank-you event and lucky prizes are small ways of expressing appreciation and motivating  these committed MCLCAs.

    - Secondly, by way of enhancement of the “Personal Selling” experience and  personal care received by a possibly pregnant women when she engages a midwife at the first ANC <4W visit. This involves in-situ in-clinic re-training of midwives by their supervisors  in the “human” dimension of personal care: how clients are greeted, and welcomed, and made to feel wonderful, especially if it turns out that the client is indeed pregnant. As part of the exchange between midwife and client is the handing over of a special Pregnancy Welcome Kit which will include simple gifts (possibly a T-shirt, or cosmetics) This should be given even a pregnancy cannot be confirmed. One might as well begin an appreciation for antenatal care from now. The Pregnancy Welcome Kit will include a small simple booklet on key topics in antenatal care, including birth preparedness, and watching out for danger signs, plus nutritional advice. (This could be the same booklet or a modified one being now prepared for distribution to newlyweds at marriage ceremonies.)  In addition, each midwife will have available two gold stars stickers: an Iron Follate Gold Star,  and an NTP Gold Star. As each of these services are provided and guidelines met, then on the cover of the Kit, each Gold Star is stuck above the woman’s name, prominently indicating she is a  “loving care” mother in the making. The Kit becomes the centerpieces for discussion between the client and the midwife. And the training of the midwife will include role playing sessions which allow them to practice going through the Kit with a client.

  - This “personal selling” will be supported by a media-based public relations campaign comprising sustained press activity during the year, short 15 sec “filler” radio announcements to be used by radio disc jockeys (DJs) in between musical pieces on radio, thematic insertions in existing radio/TV local drama serials, and radio and television discussion/chat shows with telephone call-in and done before live audiences.

    - The press activities will consist of a <4W launch press conference, followed by three press conferences during the course of the year, covering key aspects of the behavioural messages and rationale and any progress results. The launch press conference should be hosted by the highest possible MOH official, if not the Minister himself and/or the wife of the Prime Minister or King. At the launch arrangements should be made to have the highest official actually hand over a  Pregnancy Welcome Kit (to be described later) to a pregnant woman and husband. Each press conference should have ready for distribution a news release or long feature article with human interest dimensions and photographs, such as the expressed delight of a woman being NTP, or early action on a danger sign saving a life, or a woman relieved that she took her iron tablets, etc. These should be prepared by contracted writers/free lance journalists. Each press conference should provide an opportunity for journalists to ask questions of key technical experts. A simple reception should be held at each press conference. In addition, every month a feature story should be written by a contracted writer/journalist, again with a human interest dimension and reflecting the different aspects of the behavioural theme and rationale, and made available to the newspapers.

    - Arrangements should be made for three radio talk/chat/discussion shows (one every four months) on the national radio network, one hour long, with a panel of two antenatal experts, and a telephone call-in component. The first three questions should be pre-arranged with colleagues to call in to get the discussion going. Similarly, three television calls-in chat/discussion shows should be organised with the National Television system. It would be best if these radio and television shows are existing talk shows dedicated on these three occasions to <4W antenatal  care. Both radio and television shows should be done before a live audience, inviting questions from the audience also. These features (the live audience and call-in) provides for the phenomenon known as “vicarious interaction” which makes people feel they are part of the on-going conversation and this facilitates internalization of the behavioural messages. (National radio and television is suggested since these will more likely  reach the critical rural audience which constitutes the majority of Cambodia and a key market for the behavioural theme, presuming that signals can be received. Other more popular media outfits may also be used in a similar fashion depending on availability and costs.)

    - A short 8-minute video should be produced on the behavioural theme, beginning with a congratulatory note for possibly pregnant women, suggesting the recommended behaviour and then providing the rationale. There should be a combination of expert inserts and testimonials from women who had a great pregnancy and birth, linked to their early start of antenatal care and continuing thereafter.  This video should be used at the beginning of the television talk shows and should then lead to discussion and questions from the audience or called-in. It may also be used by the television documentary departments of the various TV channels for insertion in other health-related documentary shows.

  - A national advertising campaign will also be an integral part of the COMBI Plan. This is further detailed later in the plan. It will consist of a minimum of 4 three-week flights of advertising during the course of the first year, done in M-RIP (Massive, Repetitive, Intense, Persistent) style via radio, television and newspapers. The national advertising effort is intended to keep on the public agenda the theme of <4W and generate mass reinforcing support for its practice, and to lend support for the door-to-door work of the MCLCAs.

    - The campaign will consist of  4  three-week spurts (or flights), during the year, with radio advertising consisting of 60-second and 30-second spots played 6-8 times per day for 5 days per week in each flight,  television spots  (60 seconds and 30 seconds) 2-3 times per evening five days per week in each flight and full-page print advertisements during the first week of each flight. Preferably a competent local advertising agency could be used; one possibility is the BBC World  Trust treated as an “advertising agency”. The advertising should be heavily discounted but they will be paid for to ensure broadcast of the spots at specific times and placement of print ads in pre-selected locations in the newspaper. The national broadcasting facility should be used but private media may also be part of the campaign, if funds allow.

  - Point-of-Service promotion should also form part of this COMBI Programme. This will take four forms:

    - A <4W Flag done up in the colours of the new logo and with the new logo should be posted at each of the 1000 health facilities where a possibly pregnant woman can go for care. The flag is not to be in the standard style of national flags but more in the shape of danglers, 45 cm by 120 cm, with the dangler hanging with the long end in vertical position. The flag becomes a visual reminder to people passing by that this is where they can come in for the <4W visit; this is where they should come within 4 weeks of having missed their period .

    - In each health centre, at the entrance way there should be three large posters prominently displayed which extend a congratulations to those possibly pregnant women (who have missed their period) and  with big tick-offs reminds the woman of the three things she should make sure she does: NTP, iron follate supplements, the Welcome Pregnancy Kit with the gifts.

    - In the midwife’s  room, there should also be the same three posters, as reminders to the midwife and the woman of the four key things they needs to deal with.

    - At each of the 1000 health facilities, every four months, on a date fixed for the entire country in that trimester, ten (10) coloured <4W balloons will  be blown up and flown high above each facility.

  - The “Welcome to Pregnancy” Kits and Midwife/Client Communication at the first ANC <4W visit: This first visit is the most critical of all the visits by the possibly pregnant client to the midwife’s office. What happens here is central to all the other behaviours we may wish to recommend for improved and maternal and child health.  A special  Welcome to Pregnancy Kit should be produced, 500,000 copies. The Kit could be the usual presentation folder which opens out with a pocket on either side. More expensively, it could be a cloth-type bag/purse of the same size as a presentation folder and which can hold A-4 size sheets. Either could be co-sponsored and funded  by a cosmetics company such as Avon, with some product samples.  The Kit should have a congratulatory feel to it. It should be presented with joy and a congratulatory exclamation from the midwife to the client, with even a hug thrown in. As the client opens the kit, there should be some simple gift for the woman (cosmetics?). In addition to the gift, there will be four single-page  sheets: one on iron follate supplement, one on NTP, one on Nutrition during Pregnancy, and another on the twelve danger signs. Each sheet should provide in simple non-technical language the value of each action. On the cover will be a space for boldly writing in the name of the woman, and atop the name three blank circles which will hold two peel-off Gold Star stickers, one each for NTP, and Iron Follate Supplementation. As the woman completes each process, she gets a Gold Star affixed to the spot on the cover. On each of the four sheets there will be a large box at the top left hand corner which the midwife ticks off as she goes through each sheet with the client. Each sheet explains what is being recommended and why. After the iron follate sheet is explained, the midwife  asks if there are any questions and after those are discussed, the midwife provides the iron follate tablets immediately for first consumption . The same review is done for the NTP Sheet. The Nutritional Advice sheet is also covered and ticked off. And so too the sheet on the twelve dangers signs and what should be done. The midwife should constantly invite the woman to ask any questions and should engage the women in responding to these questions. Finally, the midwife shows the gifts and hands over the kit to the woman with a smile and wishing her a wonderful pregnancy. If it is not yet possible to confirm pregnancy, the above process should still be carried out, with an invitation to the woman to return to check on whether she is in fact pregnant.  For all women, the midwife should conclude by setting a time for the next visit.

  - The COMBI Programme will begin with administrative mobilisation (official memoranda/circulars from the Minister of Health and other senior officers, and associated staff meetings) and directed at engaging all 50,000 (check number??) MOH  staff at all levels (the center, provincial, district, and including the lowest level staff, such as cleaning staff)  in Cambodia , to actively participate in this COMBI effort for <4W early antenatal visit.

  - A Business Partnership for Mother and Child Loving Care will be created and will comprise representatives of selected business companies in Cambodia such as a national cell phone company, an agricultural development  bank and/or other banks, supermarket companies, and others. These partners will be invited to fund different components of the proposed COMBI Plan (such as providing gifts for the MCLCAs, with discreet acknowledgement given for their contribution.

  - The COMBI Plan will be managed by a team comprising officers from the MOH and its National Maternal and Child Health Programme, the National Immunisation Programme, and the National Center for Health Promotion; UNICEF/Cambodia, WHO/Cambodia, UNFPA/Cambodia; representatives of the national radio-tv system; and selected other partners. This group to be called the Implementation Group will be  under the chairmanship of a senior officer of the MOH/NMCHP.  One senior staff  member of the NCHP should be designated the chief staff person responsible for coordinating day-to-day execution of the programme. This COMBI Coordinator will be supported by a new hire to be called the COMBI Manager attached to UNICEF but working within the NCHP with the COMBI Coordinator. The COMBI Manager will deal with the fine details of implementation. This Implementation Group will meet once per week in the first four months of the programme and afterwards once per month, for coordinating implementation and monitoring implementation progress,

  - Impact Evaluation: This will take various forms:

    - Behavioural impact will be evaluated by way of analyzing the data gathered from all health centres as to the timing of when possibly pregnant women show up at the centers for their first ANC visit during the first year of the programme, comparing the results to previous years and the DHS 2005 results. The NMCHP will ensure that each health facility is capable of tracking and recording this basic information regarding the timing of the first ANC visit, in relation to the behavioural objective of this COMBI Plan.

    - A baseline sample survey of  six provinces (covering rural and urban communities) will be carried out to obtain a current baseline as to how soon after missing one’s period does a woman visit  midwife at the nearest health centre. A follow-up survey 12 months later will also be carried to track changes.

    - A mid-project tracking survey (small random samples of about 100 each) in four communities will track exposure to and comprehension of the behavioural theme, and any emerging behavioural responses.

  - It is widely acknowledged in the private sector world of integrated marketing communication, the consumer communication  world, that behavioural responses are possible only with a smart blend of mass media, personal selling/interpersonal communication, promotional triggers and related public relations/advocacy. The COMBI Plan as detailed below may seem an excessive and messy blend. But it follows the recommended style of M-RIP: Massive, Repetitive, Intense, and Persistent. And all of it is necessary. In marketing communication experience, there is the view that to have behavioural impact, an individual needs to be “hit” with the behavioural message about 6 times per day over several days per week over several weeks. The above strategy should lead to the following “hits”:

An individual will get the <4W behavioural message from the media advertising, from a poster in the health center, from the home visit by a MCLCA, from a flag at each health service point, from a radio” filler” announcement, from a radio call-in show, from a television call-in show, from a news story in the press, from a family member or neighbour who would have seen/heard the behavioural message from some source.

Non-COMBI specialists are likely to be tempted to eliminate several communication interventions if budget crunches appear. It is important that, if there is a budget crunch, decisions on what blend of communication interventions to retain be made by COMBI specialists in close consultation with the MOH/NMCHP/NIP/NCHP and UNICEF staff. In addition, we should avoid the temptation of carrying out the programme in piece-meal fashion, meaning that we’ll do some personal selling this month, and then sometime later we’ll have a press article and a press conference, and then later in the year we’ll do some advertising, etc. Ideally, this integrated  plan should be synchronised and strategically implemented so that the different pieces providing reinforcing support to each in a timely fashion.

4.  Communication Actions

(Note: Each of the actions below will require their own implementation micro plans; in preparing the detailed work plan, under each activity, one should therefore insert a line for developing the micro plans.)

  - New Branding of TTE/Early Ante Natal Care Visit: <4W

    - Design a new logo and branding them for the recommended behaviour.  See guidelines in section 3 above. This is to be used on all materials dealing with tis COMBI Plan  in Cambodia.

    - Develop a micro plan for this activity, perhaps involving a selected local design firm, or running a competition among design/advertising agencies, with a fixed monetary prize for the winner.

  - Administrative Mobilisation

    - Carry out a programme of activities  for Administrative Mobilisation, consisting of staff meetings and consultations, and the widespread, extensive distribution of  memoranda/circulars.

      - Prepare a two-page briefing paper in Memorandum format with the <4W logo signed by the Minister of Health, possibly with his photograph. The memorandum should describe the new thrust in antenatal care and TTE in Cambodia with the and the COMBI Plan to be implemented with its behavioural focus. The memo should begin  with an expression of appreciation for the past work done on TTE and antenatal care by health staff but drawing attention to the remaining challenges, and calling for continued vigorous support of the COMBI initiative focused on the specific desired  behavioural outcome. The briefing memorandum is to be distributed to all staff at all levels in the MOH.

      - Print 50,000 copies of the Briefing memorandum, single page, both sides, with the new logo , on coloured stock with one additional colour, or two colours on white stock.

      - Hold joint meeting with Cambodia Minister of Health and other senior officers of the MOH including staff of the NMCHP, NIM, NCHP.  Share briefing paper and further explain COMBI Plan to be implemented. This meeting is to secure and confirm commitment at the most senior level of the MOH.

      - Hold meeting between the Minister of Health, other senior officers of the MOH including officers of the NMCHP, NIM, NCHP , all Provincial Health Chiefs , as part of one of the MOH regular meetings with these officers. Share briefing paper with the COMBI Plan summary and discuss implementation. Secure commitment for implementation, with a special focus on the help expected of all health staff in sharing the behavioural message. Each Provincial Health Chief will be asked to ensure that the briefing memo is circulated throughout the provincial health system and that regular staff meetings at all levels (and incorporating all staff,(including cleaning and building maintenance staff) include the Minister’s memo on the agenda for discussion.

      - Issue an official memorandum from the Director of the NMCHP on the COMBI Plan and the expected help of each midwife to be individually addressed to each midwife, explaining the rationale for the Plan and requesting their involvement and support, specifying the actions they will need to take when someone comes in for their first ANC visit s recommended, and their role as trainers/mentors of MCLCAs.

      - Issue an official memorandum from the Minister/MOH to each Provincial Governor/Municipality Chief (copied to the appropriate Minister responsible for provincial/municipality government actions) explaining the new COMBI Plan for TTE/Ante Natal and inviting their keen support and involvement. The Minister will request that each Provincial Governor set up a special Task Force which will ensure implementation of the COMBI Plan activities at the provincial level.

      - Check that Health Center directors have held in-house meetings as requested. Check that information to all staff at the District and Sub-District and “lower” levels have been delivered, through written memorandum and/or through one of the regular meetings of staff.

      - Develop micro implementation plans for each of the above activities

  - Public Relations

    - Carry-out a programme of Media-Based Public Relations Promotional activities  to put on the public agenda the issues surrounding TTE/Ante Natal Care and the <4W recommended behaviour in Cambodia and why Cambodia MOH is taking special intensive action, and what specific behaviour is being urged:

      - Contract a freelance writer/journalist.

      - Prepare a two-page press release (written in journalistic style) and based on the briefing memorandum, announcing plans to embark on a COMBI strategy to encourage <4W behaviour for TTE and Ante Natal Care, and explaining why Cambodia Government/MOH is taking special intensive action.

      - Hold press conference, and an extended press briefing following the formal press conference to announce the launch of the COMBI Programme and the behavioural objective, for the Minister of Health and senior officials of the MOH  and the NMCHP, NIM, and NCHP, with a small press kit comprising press release and background documents  for distribution to the media representatives, including general information on maternal and child health in Cambodia.  MOH technical staff should conduct the press briefing which should follow the press conference and should be about an hour long. Staff should be prepared to respond to queries about the MCH situation and questions regarding the rationale for the specific <4W behaviour being recommended.

      - Prepare and distribute to print media in Cambodia  a major press release of a 2000-word feature article on the MCH/TTE/Ante Natal Care situation in Cambodia based on the briefing document but written in journalistic style and featuring various quotes from Cambodia MOH staff (men and women),  and others, including UNICEF, WHO and UNFPA staff in Cambodia. The feature article should be supplemented by photos and should address the key questions that are popularly asked about TTE/Ante Natal Care and especially the <4W behaviour. The feature should anticipate popular questions to be asked.

      - Prepare and distribute for radio and television a 2-minute press release with sound/video bites from the MOH covering some of the same themes as the feature article/press release above, for use in radio-television news programmes.

      - Prepare every month at least one 1500-word feature article to be offered and hopefully to appear in each of the major newspapers, covering some aspect of MCH/TTE/Ante Natal Care/<4W  or some aspect of the COMBI Programme, such as the start of the personal selling, or  personal stories and testimonials (with photos) of people carrying out the recommended behaviour and benefiting as a consequence with safe births and healthy babies.

      - Produce and broadcast three one-hour radio discussion programmes with invited telephone call-in on Cambodia National Radio, once every four months. The show hosted by a good moderator and two articulate MCH specialists (one male, one female) should discuss various issues related to  MCH/TTE/Ante Natal Care/<4W  but with special emphasis on the key behavioural message. The show should be done in front of a small live audience if possible. The show should try for a blend of music and chat. Some of the telephone calls should be pre-arranged to get the process going.

      - Produce and broadcast three one-hour television discussion shows with telephone call-in on Cambodia National Television, similar in format to the radio discussion show, once every four months. This show should be done in front of a live audience if possible.

      - Produce an 8-minute video focused on the behavioural theme and rationale, and distribute to all television stations.

      - Arrange to use the 8-minute video as a trigger for discussion on the television chat/call-in show discussed above.

      - Arrange for the behavioural theme to be raised/presented in existing drama shows on radio-TV at least once every four months during the year.

      - Prepare ten (10) 15-second sound bites in scripted form covering ten different aspect of the <4W behavioural message. These are to be used as “fillers” by radio disc jockeys (DJs) to fill time in between playing musical selections. For e.g., after a record is played, the DJ says, “Hello, you wonderfully pregnant women in Cambodia. Remember to take your iron follate tablets…and here’s why……etc, etc….”  or “We know this is a sensitive private matter but it is very important. If you have missed your period, you could be beautifully pregnant-- don’t wait too long -- within the next four weeks, go see a midwife at your health centre…they have a gift for you…”

      - Distribute the pack of 10 “filler” scripts to each radio station with a request that the DJs use them from time during the day (as a public service for antenatal care and saving the lives of mothers and babies), preferably about 8 times during the day, either repeating the same filler or mixing them. The radio stations should be urged to use these fillers over one two week period to be specified/suggested  in every three months.

      - Re-send the same pack of 10 “fillers” or slightly modified ones just before the specified two week period  in every three months/quarter (with a reminder note and specifying the desired two weeks for the use of the fillers) to all radio stations

  - Personal Selling/Door-to-Door Communication

    - Mother and Child Loving Care Ambassadors (MCLCAs) Home Visits

      - Prepare and send a memorandum from the Minister of Health (or senior official) to all 1000 directors of health centres (copied to Provincial/District Health Chiefs) once more outlining the MCH situation and challenges, the COMBI Programme and the new <4W thrust and the   behavioural message to be promoted, and calling for their keen, passionate involvement. The memo should thank them for the excellent past efforts. The memo should then proceed to spell out the expected roles of midwifes and the identification and operation of a designated core of volunteers (one per village for each of the 13,500 villages), preferably selected from existing health volunteers on the Village Health Volunteers Team who will serve as MCLCAs, as described in Section 3 above. The memo should direct each health centre director in consultation with the midwife to select an MCLCA from among the existing core of volunteers, and make arrangements for designating their areas of coverage and the number of household to be visited, as detailed in Section 3, for house-to-house sessions. The memo should stress the role of the midwife as a Mentor  and informal supervisor of the MCLCAs.

      - Design and produce 16,000 plastic pin badges, in the logo colours and with the logo to be given to all midwives and MCLCAs. MCLCAs will wear these badges when visiting homes; and the midwives will also wear them at work.

      - Design and produce 13,500 coloured light cotton “waist vests” (a sort of jacket which one wears over a shirt or dress, like the safety vests some police/traffic officers wear but not necessarily in that expensive fluorescent material), emblazoned with the <4W  logo and the MCLCA title . These are to be given to the MCLCAs to wear when they make their home visits.

      - Write, design and print 2.5 million copies of a <4W Advisory, A-4 size, two-sided , single sheet, two colours, with content as described in Section 3 above, with the focus on the behavioural message and rationale.  These are to be distributed door-to-door by the MCLCAs. Section 3 provides a description of the content of the Advisory Sheet with the quiz on the back.

      - Design and print 13,500 Certificates of Appreciation, to be electronically signed by the Minister of Health, to be given out to the MCLCAs at the Thank You ceremony to be held close to the end of the first year.

      - Prepare a 4-page Training Memo to be sent to each Health Centre Director and Midwife with instructions and guidelines on how to carry out a two-day non-residential training of MCLCAs with regard to the <4W behaviour and its rationale, with special emphasis on role-playing of the door-to-door-visits by MCLCAs. (The Health Centre Director and Midwife have been involved in sufficient MCH training and so no additional training for them is intended. On the basis of the Training Memo they should be able to carry out a simple training exercise for the MCLCAs.)

      - Arrange for the MCLCAs to undergo two one-day non-residential training at each health centre conducted by the midwife and the Health Centre Director.  A lunch and tea/coffee breaks will be served for the MCLCAs. At the training, each MCLCA will be given their badge, vest, and  <4W Advisory Sheets.

      - Arrange for the MCLCAs to meet with their Health Centre Directors and midwives at each health centre to plan/schedule their home visits in their designated areas, and at this meeting the badges and Advisory Sheets should be distributed, and the MCLCAs should discuss once more exactly what they will do at each home visit to stress the behavioural theme.

      - Arrange for the home visits by the MCLCAs to begin in about the second month of the COMBI Programme, at the same time throughout the country.

      - Arrange for press coverage of the launch of the MCLCAs’ work.

      - Arrange for the second round of home visits six months later.

      - Arrange for the collection of small gifts from the private sector to be distributed to the MCLCAs on 4 occasions in the year.

      - Hold a modest community social (simple refreshments) event at the district or sub-district level in the first three month of the COMBI Programme under the auspices of MOH and the district medical team. Thank the MCLCAs for their home visit work and continued support, distribute gifts, and invite them to share their experiences and challenges.

      - Hold another similar community event in the second quarter.

      - Hold a similar event in the third quarter.

      - Arrange to secure 48 airline/hotel package tour prizes  -- for  Bangkok or Cambodia beach resort -- donated by the private sector for MCLCA/mentor Midwives winners to be given out as part of a lucky draw event at Provincial Thank You Ceremonies, described below.

      - Hold a Thank You Ceremony event at the provincial level for all midwives and MCLCAs with a simple meal served. At this ceremony, the Provincial Governor thanks each MCLCA for their work, distributes gifts, and gives each a Certificate of Appreciation. A lucky draw is conducted from among the names of all provincial MCLCAs present; the lucky winners (two per province) are given the airline/hotel tour packages as their prizes.

    - Midwife/Client Communication at the first ANC <4W Visit  and the “Welcome to Pregnancy” Kits

      - Arrange for preparation, design, production and distribution to Health Centres of 500,000 “Welcome to Pregnancy” Kits as described in Section 3 above, including the Gold Star stickers.

      - Arrange for a memo to be sent by the Director/NMCHP to each midwife and Health Centre Director (copied to appropriate others) once more thanking them for their support of this COMBI Plna and setting out clear guidelines and instructions with regard to that first <4W ante natal care visit, what should be done by the midwife and how to use the Welcome to Pregnancy Kit, including the Gold Star stickers as mentioned in section 3. The memo should request that The Health Centre Director and the midwife should schedule a two-hour orientation session to go over the guidelines and instructions.

      - Check that the orientation session mentioned above has taken place.

      - Arrange for random monitoring of health centres to examine the work of midwives with regard to  the <4W visit.

  - Advertising

    - Plan and execute an M-RIP  (Massive, Repetitive, Intense, Persistent) Radio-TV- Newspaper advertising campaign (to be carried out in collaboration with an “advertising agency” to be contracted by MOH/NCHP/UNICEF).

    - Make arrangements for selecting an “advertising agency”, including sending out a creative brief (based on this COMBI Plan) and having invited agencies make short presentations on their creative treatment. (The BBC World Trust can be treated as an advertising agency for these purposes.)

    - Confirm “flight” scheduling of campaign allowing for 4 flights of 3 weeks duration during the course of one year with breaks/pauses between the flights ranging from 2-6 weeks . (The advertising campaign will be carried out in “flights” over the one-year period. A flight is defined as that period of time during which the advertisements take-off or are run (say three weeks), followed by a pause of several weeks (about 2-6 weeks), and then followed by another flight of  another three weeks, another pause, and so on. Strategic and constant repetition is key in advertising.  The ads, reinforcing each other in each medium, will reach key opinion leaders (KOLs)  who in turn further disseminate the messages and stir interpersonal chat. )

    - Confirm agreement on style of advertising. The electronic media advertising should avoid excessive creativity, gimmickry and frivolity (excess of music, dance, cleverness, etc.). We are dealing with serious themes and while some humour/music can be there, the advertising should have the air of an intimate conversation with the listener/mother, husbands, in-laws, grandmothers, especially the rural listener, an act of engaged communication. Simple, elegant production values are needed. These spots should be earnest, calm, very intimate chats with the audience. On radio and TV one is always communicating with just one other individual. Intimacy is important for the critical subject of  pregnancy and mother-child loving care. The content of all the ads should focus on the behavioural response being sought with precise and intimate explanation of why the behaviour is being recommended.

    - Develop content of the advertisements for radio, television, newspapers with reference to the themes of Section 3 above. The advertisements should focus sharply on the behavioural theme,  and the rationale for the behaviour. The behavioural theme should be stressed at least three times in each ad.

    - Produce 60-sec and 30-second versions for radio and television advertisements, and half-page for newspapers. It may be necessary to produce two or three different spots for radio and TV in order to incorporate the key themes listed in Section 3 above. Some of the spots should refer to the planned home visits by MCLCAs.

    - Arrange for placement of ads on radio-television, and newspapers. In the first flight, 60-second radio and television spots should be used for the 3 week flight, five days per week. Radio spots should be scheduled for 8 times per days, and TV spots  three per evening. In the other 3  3-week flights, the schedule should remain the same except that 30-sec spots may  be used on radio-TV .Note: MOH should engage in formal negotiations with the media on advertising costs and should request heavily discounted rates. This could include some free spots in relation to paid spots. The selected advertising agency can advise on best media to use but do note the need to reach the large rural population.)

    - Monitor implementation of radio-television-newspaper advertising and make adjustments depending on public feedback and results of small tracking surveys (described below under “Impact Evaluation”).

  - Point of Service Promotion

    - Produce 1500 <4W Flags/Danglers as described in Section 3 above and arrange to have these danglers/flags flown at each health facility providing antenatal care.

    - Produce 10,000 posters on the behavioural theme and focusing on the three major sub-components (NTP, iron follate, and danger signs) as described in Section 3 and arrange to have these posters placed as described in Section 3 at health centres (three, each right next to each other, in the entrance way of the health centres and three similarly posted  in the midwife’s room.)

    - Produce 40,000 coloured  <4W balloons and arrange to have these blown up and flying high above each health facility providing antenatal care during a fixed time period four times per year.

    - The Business Partnership for Mother-Child Loving Care

      - Establish a Business Partnership by inviting representatives of selected business corporation as mentioned in Section 3.

      - Arrange with the partnership the donation of small gifts to be given out to MCLCAs four times per year.

      - Arrange with the partnership for the Tour Prizes for the Lucky Draw event at the Thank You Ceremony.

5. Impact Evaluation

  - Arrange for behavioural impact evaluation based on service statistics which monitor the time at which presumably pregnant women visit the midwife for the fist time.

    - Develop micro plan for ensuring data collection system exists and operates at each health centre.

  - Conduct baselines sample survey for obtaining behavioural measures (self-reported) in a sample of 6 provinces as discussed in Section 3. (Will need separate micro plan)

  - Conduct mid-project tracking survey in 4 communities  to track exposure and comprehension of measures and any behavioural trends.  (Will need separate micro plan). Results of the tracking surveys will be used to re-shape the communication effort, if necessary.

  - Conduct end-of-first year sample survey in the same six provinces as selected  above to obtain behavioural measure.

6. COMBI Programme Management and Work Plan

  - Management

  - The COMBI Plan will be managed by a team comprising officers from the MOH and its National Maternal and Child Health Programme, the National Immunisation Programme, and the National Center for Health Promotion; UNICEF/Cambodia, WHO/Cambodia, UNFPA/Cambodia; representatives of the national radio-tv system; and selected other partners. This group to be called the Implementation Group (IG) will be  under the chairmanship of a senior officer of the MOH/NMCHP.  One senior staff  member of the NCHP should be designated the chief staff person responsible for coordinating day-to-day execution of the programme. This COMBI Coordinator will be supported by a new hire to be called the COMBI Manager attached to UNICEF but working within the NCHP with the COMBI Coordinator. The COMBI Manager will deal with the fine details of implementation. This Implementation Group will meet once per week in the first four months of the programme and afterwards once per month, for coordinating implementation and monitoring implementation progress.

    - Appoint the IG

    - Appoint the COMBI Coordinator

    - Recruit the COMBI Manager

    - Schedule and hold meetings of IG.

  - Work Plan

    - The above list of communication and managerial actions in Section 4, 5, 6 will be laid out in a detailed implementation work plan with appropriate scheduling of activities and identification of persons responsible for implementation at all levels. This exercise should be a group exercise involving the many individuals who will be involved in implementation, including the proposed IG.  (The above activities will be repeated below in Annex I as a tentative Work Plan but laid out in landscape format with columns  for designating persons responsible and setting time lines.)

    - OVERVIEW OF Cambodia NTP- Ante Natal Care COMBI PLAN

October, 2007 – September, 2008

- Behavioural Objective:

To have 95% of all women who have missed their menstruation/period visit the nearest Health Centre and meet with a doctor/nurse/midwife, within four weeks of missing their period to receive a “package” of health care services (to be defined later and which will include TT vaccination or other assurance of NTP based on previous vaccinations, plus  iron follate  supplementation, nutrition advice and  birth preparedness tips, ), on the presumption that they might be pregnant or on the confirmation by physical (manual palpation of the uterus) examination that they are pregnant, and in this way have at least 85% of all  pregnant women (340,000 ) receive NTP, among other MCH benefits.

- COMBI Strategy and Interventions:

SUMMARY OF COMMUNICATION INTERVENTIONS

NTP/Ante Natal Care: Singular Behavioural Theme

“Missed your period? If yes, then come on in to our health centre and see a midwife immediately—

Don’t wait—come in within the next four weeks. We have a special gift for you if you are pregnant ”

- Branding of Behaviour: Develop new logo—suggested “<4W”..

- Administrative Mobilisation: Memos to all staff in MOH, Staff Meetings,  other administrative meetings ,district level meetings of  field level health staff—all levels and all staff to be covered.

- Public Relations/Media-Based Promotion:  Feature articles, radio-TV talk/call-in discussion shows, video, Press Conferences and Press Briefings, and “filler” announcements by DJs on radio; possible insertions in radio-TV dramas.

- “Personal Sellers”: 4,000 volunteers from existing core of health volunteers to be branded “Mother and Child Loving Care Ambassadors” (MCLCAs) will visit every household in Cambodia and leave behind a <4W Advisory sheet; about 2000 midwives and other health staff engaging warmly and sensitively women coming for their first antenatal care visit within 4 weeks of missing their period, using the Welcome to Pregnancy Kits, including gifts for the women. These special kits will be prepared for each pregnant woman.. The kits will have a congratulatory feel  and a gift for the mother-to-be. Also  included will be four  information sheets on NTP, iron follate supplements, nutrition, and the danger signs and what to do. Thank You social events  for MCLCAs and midwives with Certificates of Appreciation distributed, and Prizes  of tours of Bangkok or Cambodia beach resort areas for lucky draw winners at the Thank You ceremonies.

- Advertising: Radio, Television, Newspaper  Advertising— four  3-week flights /year, 8 radio spots per day and 3 TV spots per evening, five days per week in each flight, with half page advertisements three times per week in the first week of each flight

- Point of Service Promotion: Dangler flags will be posted at all health facilities; once every three months <4W   balloons will fly above these facilities;  behaviourally-focused antenatal care posters will be posted in all health facilities, at the entrance way and in doctors’ offices as reminders of the behavioural themes to be covered on that first visit of a pregnant woman to the health facility.

- The Business Partnership forMother-Child Loving Care: . A partnership of business representatives will established—for generating small gifts for MCLCAs, prizes for the Lucky Draw, and other co-sponsorship.

- Notes:

  - Carry it out in M-RIP (massive, repetitive, intense and persistent) style.

  - Work for combined effect of multiple interventions – six impressions in short time period for behavioural impact.

  - Management: Ministry of Health/ NMCHP/NIM/NCHP with UNICEF, WHO and UNFPA, under day-to-day management by NCHP.

  - Budget: One year - US$ 163,200

# Budget				October 2007 – September 2008    	US $

Note: This is a tentative estimate of costs and will need to be refined. One emphasises: Effective communication for behavioural impact, unfortunately, cannot be done on the cheap. This budget also presumes the usual counter-part contribution of the MOH in terms of logistics, etc. The budget will be reformulated and so too the COMBI activities when there is a clearer sense of exactly what funds are available and exactly what activities are to be implemented. Materials production costs are based on printing outside of Cambodia for bulk quantities, such as in China, with all design work done, of course, in Cambodia in Khmer.

### New Logo Design				             	 	          1,000

### Administrative Mobilisation

### 50,000 copies of  Briefing Memo                                                          2,000

### Meetings, travel, refreshments                                                           	4,000

Sub-Total:	           6,000

### Media Promotion

# Press Conferences/Refreshments	1,000

# Feature Articles Writing and other press                                               2,000

# release productions

# Radio Call-In /Discussion Shows   - Honorarium                             	1,200

# Television Call-In/Discussion Shows- Honorarium                              1,500

# Writing and distribution of “filler” announcements	1,000

7.3.6	8- min Video						           3,000

Sub-Total: 	9,700

### Personal Sellers: MCLC Ambassadors and Midwives

# 6,000 Thank You Certificates	1,000

# 2.5 million <4W Advisory Sheets                                                       15,000

    - Thank You Social Event (Partial) Costs  	8,000

    - 16,000 plastic pin badges for MCLCAs/Midwives                                8,000

    - 13,500 coloured light cotton vests with logo                                        20,000

    - Training Guidelines for Midwives                                                    	   500

    - Training Sessions for MCLAs: Materials/Meals	6,000

    - “Welcome to Pregnancy” Kits -500,000 with Gold Stickers               30,000

( Co sponsors to provide additional funds for the kits)

Sub-Total:                      88,500

# Advertising

7.6.1	Radio-TV-Newspaper Advertising (discounted, co-sponsored)	          20,000

### Point of Service Promotion

    - 10,000 posters                                                                                        4,000

    - 40,000 <4W balloons	2,000

    - 1,500 Flags/Danglers	3,000

Sub-Total:                              9,000

### Evaluation/Research

### Analysis of Service Data	2,000

### 4  Small Tracking Surveys	3,000

### Baseline Sample Survey—6 provinces	5,000

### Post-1 Year Sample Survey—6 Provinces	5,000

### Sub-Total:                    15,000

### Management

7.8.1 COMBI Manager						         10,000

7.8.2 Administrative Costs	 (beyond counter-part contribution)		           4,000

Sub-Total: 	          14,000

GRAND TOTAL:                  US  $163,200

Annex I: Cambodia TTE/NTP/Ante Natal Care COMBI Work Plan: October  2007 – September  2008

(To be completed in group exercise with implementing staff)

SUMMARY OF COMMUNICATION INTERVENTIONS

NTP/Ante Natal Care: Singular Behavioural Theme

“Missed your period? If yes, then come on in to our health centre and see a midwife immediately—

Don’t wait—come in within the next four weeks. We have a special gift for you if you are pregnant ”

- Branding of Behaviour: Develop new logo—suggested “<4W”..

- Administrative Mobilisation: Memos to all staff in MOH, Staff Meetings,  other administrative meetings ,district level meetings of  field level health staff—all levels and all staff to be covered.

- Public Relations/Media-Based Promotion:  Feature articles, radio-TV talk/call-in discussion shows, video, Press Conferences and Press Briefings, and “filler” announcements by DJs on radio; possible insertions in radio-TV dramas.

- “Personal Sellers”: 4,000 volunteers from existing core of health volunteers to be branded “Mother and Child Loving Care Ambassadors” (MCLCAs) will visit every household in Cambodia and leave behind a <4W Advisory sheet; about 2000 midwives and other health staff engaging warmly and sensitively women coming for their first antenatal care visit within 4 weeks of missing their period, using the Welcome to Pregnancy Kits, including gifts for the women. These special kits will be prepared for each pregnant woman.. The kits will have a congratulatory feel  and a gift for the mother-to-be. Also  included will be four  information sheets on NTP, iron follate  supplements, nutrition, and the danger signs and what to do. Thank You social events  for MCLCAs and midwives with Certificates of Appreciation distributed, and Prizes  of tours of Bangkok or Cambodia beach resort areas for lucky draw winners at the Thank You ceremonies.

- Advertising: Radio, Television, Newspaper  Advertising— four  3-week flights /year, 8 radio spots per day and 3 TV spots per evening, five days per week in each flight, with half page advertisements three times per week in the first week of each flight

- Point of Service Promotion: Dangler flags will be posted at all health facilities; once every three months <4W   balloons will fly above these facilities;  behaviourally-focused antenatal care posters will be posted in all health facilities, at the entrance way and in doctors’ offices as reminders of the behavioural themes to be covered on that first visit of a pregnant woman to the health facility.

- The Business Partnership for Mother-Child Loving Care: . A partnership of business representatives will established—for generating small gifts for MCLCAs, prizes for the Lucky Draw, and other co-sponsorship.

.

NOTE: Numerous actions below will require their separate micro-plans and sometimes micro-plans for actions at the provncial/district/sub-district/village level. The activities below should there fore be modified to reflect internal micro-planning steps to be taken.

Activities				         				     				     Completion Date 		              Responsible

  - New Logo/Branding

    - Design a new logo and branding them for the recommended behaviour.  See guidelines in section 3 above. This is to be used on all materials dealing with this COMBI Plan  in Cambodia.

    - Develop a micro plan for this activity, perhaps involving a selected local design firm, or running a competition among design/advertising agencies, with a fixed monetary prize for the winnerDevelop a micro plan for this activity, perhaps involving a local design firm.

  - Administrative Mobilisation

    - Carry out a programme of activities  for Administrative Mobilisation, consisting of staff meetings and consultations,

and the widespread, extensive distribution of  memoranda/circulars.

      - Prepare a two-page briefing paper in Memorandum format with the <4W logo signed by the Minister of Health, possibly with his photograph. The memorandum should describe the new thrust in antenatal care and TTE in Cambodia with the and the COMBI Plan to be implemented with its behavioural focus. The memo should begin  with an expression of appreciation for the past work done on TTE and antenatal care by health staff but drawing attention to the remaining challenges, and calling for continued vigorous support of the COMBI initiative focused on the specific desired  behavioural outcome. The briefing memorandum is to be distributed to all staff at all levels in the MOH.

      - Print 50,000 copies of the Briefing memorandum, single page, both sides, with the new logo , on coloured stock with one additional colour, or two colours on white stock.

      - Hold joint meeting with Cambodia Minister of Health and other senior officers of the MOH including staff of the NMCHP, NIM, NCHP.  Share briefing paper and further explain COMBI Plan to be implemented. This meeting is to secure and confirm commitment at the most senior level of the MOH.

      - Hold meeting between the Minister of Health, other senior officers of the MOH including officers of the NMCHP, NIM, NCHP , all Provincial Health Chiefs , as part of one of the MOH regular meetings with these officers. Share briefing paper with the COMBI Plan summary and discuss implementation. Secure commitment for implementation, with a special focus on the help expected of all health staff in sharing the behavioural message. Each Provincial Health Chief will be asked to ensure that the briefing memo is circulated throughout the provincial health system and that regular staff meetings at all levels (and incorporating all staff,(including cleaning and building maintenance staff) include the Minister’s memo on the agenda for discussion.

      - Issue an official memorandum from the Director of the NMCHP on the COMBI Plan and the expected help of each midwife to be individually addressed to each midwife, explaining the rationale for the Plan and requesting their involvement and support, specifying the actions they will need to take when someone comes in for their first ANC visit as recommended, and also their role as Trainer/Mentor for the MCLCAs

      - Issue an official memorandum from the Minister/MOH to each Provincial Governor/Municipality Chief (copied to the appropriate Minister responsible for provincial/municipality government actions) explaining the new COMBI Plan for TTE/Ante Natal and inviting their keen support and involvement. The Minister will request that each Provincial Governor set up a special Task Force which will ensure implementation of the COMBI Plan activities at the provincial level.

      - Check that Health Center directors have held in-house meetings as requested. Check that information to all staff at the District and Sub-District and “lower” levels have been delivered, through written memorandum and/or through one of the regular meetings of staff.

      - Develop micro implementation plans for each of the above activities

  - Public Relations/Media Promotion

    - Carry-out a programme of Media-Based Public Relations Promotional activities  to put on the public agenda the issues surrounding TTE/Ante Natal Care and the <4W recommended behaviour in Cambodia and why Cambodia MOH is taking special intensive action, and what specific behaviour is being urged:

      - Contract a freelance writer/journalist.

      - Prepare a two-page press release (written in journalistic style) and based on the briefing memorandum, announcing plans to embark on a COMBI strategy to encourage <4W behaviour for TTE and Ante Natal Care, and explaining why Cambodia Government/MOH is taking special intensive action.

      - Hold press conference, and an extended press briefing following the formal press conference to announce the launch of the COMBI Programme and the behavioural objective, for the Minister of Health and senior officials of the MOH  and the NMCHP, NIM, and NCHP, with a small press kit comprising press release and background documents  for distribution to the media representatives, including general information on maternal and child health in Cambodia.  MOH technical staff should conduct the press briefing which should follow the press conference and should be about an hour long. Staff should be prepared to respond to queries about the MCH situation and questions regarding the rationale for the specific <4W behaviour being recommended.

      - Prepare and distribute to print media in Cambodia  a major press release of a 2000-word feature article on the MCH/TTE/Ante Natal Care situation in Cambodia based on the briefing document but written in journalistic style and featuring various quotes from Cambodia MOH staff (men and women),  and others, including UNICEF, WHO and UNFPA staff in Cambodia. The feature article should be supplemented by photos and should address the key questions that are popularly asked about TTE/Ante Natal Care and especially the <4W behaviour. The feature should anticipate popular questions to be asked.

      - Prepare and distribute for radio and television a 2-minute press release with sound/video bites from the MOH covering some of the same themes as the feature article/press release above, for use in radio-television news programmes.

      - Prepare every month at least one 1500-word feature article to be offered and hopefully to appear in each of the major newspapers, covering some aspect of MCH/TTE/Ante Natal Care/<4W  or some aspect of the COMBI Programme, such as the start of the personal selling, or  personal stories and testimonials (with photos) of people carrying out the recommended behaviour and benefiting as a consequence with safe births and healthy babies.

      - Produce and broadcast three one-hour radio discussion programmes with invited telephone call-in on Cambodia National Radio, once every four months. The show hosted by a good moderator and two articulate MCH specialists (one male, one female) should discuss various issues related to  MCH/TTE/Ante Natal Care/<4W  but with special emphasis on the key behavioural message. The show should be done in front of a small live audience if possible. The show should try for a blend of music and chat. Some of the telephone calls should be pre-arranged to get the process going.

      - Produce and broadcast three one-hour television discussion shows with telephone call-in on Cambodia National Television, similar in format to the radio discussion show, once every four months. This show should be done in front of a live audience if possible.

      - Produce an 8-minute video focused on the behavioural theme and rationale, and distribute to all television stations.

      - Arrange to use the 8-minute video as a trigger for discussion on the television chat/call-in show discussed above.

      - Arrange for the behavioural theme to be raised/presented in existing drama shows on radio-TV at least once every four months during the year.

      - Prepare ten (10) 15-second sound bites in scripted form covering ten different aspect of the <4W behavioural message. These are to be used as “fillers” by radio disc jockeys (DJs) to fill time in between playing musical selections. For e.g., after a record is played, the DJ says, “Hello, you wonderfully pregnant women in Cambodia. Remember to take your iron follate tablets …and here’s why……etc, etc….”  or “We know this is a sensitive private matter but it is very important. If you have missed your period, you could be beautifully pregnant-- don’t wait too long -- within the next four weeks, go see a midwife at your health centre…they have a gift for you…”

      - Distribute the pack of 10 “filler” scripts to each radio station with a request that the DJs use them from time during the day (as a public service for antenatal care and saving the lives of mothers and babies), preferably about 8 times during the day, either repeating the same filler or mixing them. The radio stations should be urged to use these fillers over one two week period to be specified/suggested  in every three months.

      - Re-send the same pack of 10 “fillers” or slightly modified ones just before the specified two week period  in every three months/quarter (with a reminder note and specifying the desired two weeks for the use of the fillers) to all radio stations

  - Personal Selling/Door-to-Door Communication and School Promotion

    - Mother and Child Loving Care Ambassadors (MCLCAs) Home Visits

      - Prepare and send a memorandum from the Minister of Health (or senior official) to all 1000 directors of health centres (copied to Provincial/District Health Chiefs) once more outlining the MCH situation and challenges, the COMBI Programme and the new <4W thrust and the   behavioural message to be promoted, and calling for their keen, passionate involvement. The memo should thank them for the excellent past efforts. The memo should then proceed to spell out the expected roles of midwifes and the identification and operation of a designated core of volunteers one per village for each of the 13,500 villages) selected from existing health volunteers on the Village Health Volunteer Teams who will serve as MCLCAs, as described in Section 3 above. The memo should direct each health centre director in consultation with the midwife to select an MCLCA from among the existing core of volunteers, and make arrangements for designating their areas of coverage and the number of household to be visited, as detailed in Section 3, for house-to-house sessions. The memo should stress the role of the midwife as a Mentor  and informal supervisor of the MCLCAs.

      - Design and produce 16,000 plastic pin badges, in the logo colours and with the logo to be given to all midwives and MCLCAs. MCLCAs will wear these badges when visiting homes; and the midwives will also wear them at work.

      - Design and produce 13,500 coloured light cotton “waist vests” (a sort of jacket which one wears over a shirt or dress, like the safety vests some police/traffic officers wear), emblazoned with the <4W  logo and the MCLCA title . These are to be given to the MCLCAs to wear when they make their home visits.

      - Write, design and print 2.5 million copies of a <4W Advisory, A-4 size, two-sided , single sheet, two colours, with content as described in Section 3 above, with the focus on the behavioural message and rationale.  These are to be distributed door-to-door by the MCLCAs. Section 3 provides a description of the content of the Advisory Sheet with the quiz on the back.

      - Design and print 4,000 Certificates of Appreciation, to be electronically signed by the Minister of Health, to be given out to the MCLCAs at the Thank You ceremony to be held close to the end of the first year.

      - Prepare a 4-page Training Memo to be sent to each Health Centre Director and Midwife with instructions and guidelines on how to carry out a two-day non-residential training of MCLCAs with regard to the <4W behaviour and its rationale, with special emphasis on role-playing of the door-to-door-visits by MCLCAs. (The Health Centre Director and Midwife have been involved in sufficient MCH training and so no additional training for them is intended. On the basis of the Training Memo they should be able to carry out a simple training exercise for the MCLCAs.)

      - Arrange for the MCLCAs to undergo two one-day non-residential training at each health centre conducted by the midwife and the Health Centre Director.  A lunch and tea/coffee breaks will be served for the MCLCAs. At the training, each MCLCA will be given their badge, vest, and  <4W Advisory Sheets.

      - Arrange for the MCLCAs to meet with their Health Centre Directors and midwives at each health centre to plan/schedule their home visits in their designated areas, and at this meeting the badges and Advisory Sheets should be distributed, and the MCLCAs should discuss once more exactly what they will do at each home visit to stress the behavioural theme.

      - Arrange for the home visits by the MCLCAs to begin in about the second month of the COMBI Programme, at the same time throughout the country.

      - Arrange for press coverage of the launch of the MCLCAs’ work.

      - Arrange for the second round of home visits six months later.

      - Arrange for the collection of small gifts from the private sector to be distributed to the MCLCAs on 4 occasions in the year.

      - Hold a modest community social (simple refreshments) event at the district or sub-district level in the first three month of the COMBI Programme under the auspices of MOH and the district medical team. Thank the MCLCAs for their home visit work and continued support, distribute gifts, and invite them to share their experiences and challenges.

      - Hold another similar community event in the second quarter.

      - Hold a similar event in the third quarter.

      - Arrange to secure 48 airline/hotel package tour prizes  -- for  Bangkok or Cambodia beach resort -- donated by the private sector for MCLCA/mentor Midwives winners to be given out as part of a lucky draw event at Provincial Thank You Ceremonies, described below.

      - Hold a Thank You Ceremony event at the provincial level for all midwives and MCLCAs with a simple meal served. At this ceremony, the Provincial Governor thanks each MCLCA for their work, distribute gifts, and gives each a Certificate of Appreciation. A lucky draw is conducted from among the names of all provincial MCLCAs present; the lucky winners are given the airline/hotel tour packages as their prizes.

    - Midwife/Client Communication at the first ANC <4W Visit  and the “Welcome to Pregnancy” Kits

    - Arrange for preparation, design, production and distribution to Health Centres of 500,000 “Welcome to Pregnancy” Kits as described in Section 3 above, including the Gold Star stickers.

    - Arrange for a memo to be sent by the Director/NMCHP to each midwife and Health Centre Director (copied to appropriate others) once more thanking them for their support of this COMBI Plan and setting out clear guidelines and instructions with regard to that first <4W ante natal care visit, what should be done by the midwife and how to use the Welcome to Pregnancy Kit, including the Gold Star stickers as mentioned in section 3. The memo should request that The Health Centre Director and the midwife should schedule a two-hour orientation session to go over the guidelines and instructions.

    - Check that the orientation session mentioned above has taken place.

    - Arrange for random monitoring of health centres to examine the work of midwives with regard to  the <4W visit.

  - Advertising

    - Plan and execute an M-RIP  (Massive, Repetitive, Intense, Persistent) Radio-TV- Newspaper advertising campaign (to be carried out in collaboration with an “advertising agency” to be contracted by MOH/NCHP/UNICEF).

    - Make arrangements for selecting an “advertising agency”, including sending out a creative brief (based on this COMBI Plan) and having invited agencies make short presentations on their creative treatment. (The BBC World Trust can be treated as an advertising agency for these purposes.)

    - Confirm “flight” scheduling of campaign allowing for 4 flights of 3 weeks duration during the course of one year with breaks/pauses between the flights ranging from 2-6 weeks . (The advertising campaign will be carried out in “flights” over the one-year period. A flight is defined as that period of time during which the advertisements take-off or are run (say three weeks), followed by a pause of several weeks (about 2-6 weeks), and then followed by another flight of  another three weeks, another pause, and so on. Strategic and constant repetition is key in advertising.  The ads, reinforcing each other in each medium, will reach key opinion leaders (KOLs)  who in turn further disseminate the messages and stir interpersonal chat. )

  - The Point of Service Promotion

    - Produce 1500 <4W Flags/Danglers as described in Section 3 above and arrange to have these danglers/flags flown at each health facility providing antenatal care.

    - Produce 10,000 posters on the behavioural theme and focusing on the three major sub-components (NTP, iron follate supplements, and danger signs) as described in Section 3 and arrange to have these posters placed as described in Section 3 at health centres (three, each right next to each other, in the entrance way of the health centres and three similarly posted  in the midwife’s room.)

    - Produce 40,000 coloured  <4W balloons and arrange to have these blown up and flying high above each health facility providing antenatal care during a fixed time period four times per year.

  - The Business Partnership for Mother-Child Loving Care

      - Establish a Business Partnership by inviting representatives of selected business corporation as mentioned in Section 3.

      - Arrange with the partnership the donation of small gifts to be given out to MCLCAs four times per year.

      - Arrange with the partnership for the Tour Prizes for the Lucky Draw event at the Thank You Ceremony.

  - Impact Evaluation

    - Arrange for behavioural impact evaluation based on service statistics which monitor the time at which presumably

pregnant women visit the midwife for the fist time.

      - Develop micro plan for ensuring data collection system exists and operates at each health centre.

    - Conduct baselines sample survey for obtaining behavioural measures (self-reported) in a sample of 6 provinces as discussed in Section 3. (Will need separate micro plan)

    - Conduct mid-project tracking survey in 4 communities  to track exposure and comprehension of measures and any behavioural trends.  (Will need separate micro plan). Results of the tracking surveys will be used to re-shape the communication effort, if necessary.

    - Conduct end-of-first year sample survey in the same six provinces as selected  above to obtain behavioural measure.

    - Conduct Tracking Surveys (based on sample size of about 100 respondents) in 6 discrete communities (mix of urban

and rural) in different parts of at mid-campaign to measure exposure to the communication interventions, track

perceptions and understanding of the messages disseminated, and also track behaviour levels. This research activity

will be contracted out to a research firm locally. Results of the tracking surveys will be used to re-shape the communication

  - COMBI Programme Management

    - Establish COMBI Implementation  Group (IG)

    - Appoint COMBI Programme Coordinator

    - Recruit COMBI Manager

    - Hold weekly IG meetings for first four months

    - Hold monthly IG Meeting after four months.