CHINA-BEIJING

COMMUNICATION-FOR-BEHAVIOURAL IMPACT (COMBI) PLAN FOR INCREASING LEVEL OF EXCLUSIVE BREAST FEEDING FOR SIX MONTHS IN CHINA-BEIJING

#### Draft One Year Proposal (of a potential 3 –Year Programme

May, 2009– April, 2010

Prepared by:

Dr. Everold Hosein (Ph.D.)

WHO Senior Communication Advisor/Consultant

WHO/WPRO Communication Consultant

in collaboration with  Capital Institute of Pediatrics, Beijing, China

1st Draft: January 26, 2009

READER’S GUIDE

This COMBI Plan is 38 pages long (without the Annex I of 6 pages which repeats the Action Plan  of Section 4 but in landscape format to become an Implementation Plan). This can be a difficult read. It has extensive and repetitive detail but this is necessary for those who will be directly responsible for implementation.  It is also substantially more than the production of posters and pamphlets. So, with apologies, one points out that this is a long read and will require some dedicated time and attention. For those who want just a quick grasp of what the Plan is about, the following advice may be useful

For A Quick Read

If one wishes to look at just a one-page overview of the COMBI Plan, please turn to page 37 and a tentative budget on page 38.

For a Bit More

If one wishes just to look at the strategic design and its rationale without too much detail, then take a look at Section 2 and Section 3,  pages 5-28.

For Much More

And if one is actually involved in implementation, then do read carefully the details of the communication actions recommended in Section 4, pages 29-36, which is also repeated in the Annex as an operational/management tool.

And yet another way:

If you read just Section 2 and Section 3, you will have a clear sense of the behavioural objective of this COMBI Plan and the strategy (mix of communication actions) to be used to get the desired behavioural results.  And then if you’d like to see how this strategy will be operationalised, then Section 4 gives you the  details of that.

COMMUNICATION-FOR-BEHAVIOURAL-IMPACT (COMBI) PLAN FOR Six-Months Exclusive Breast Feeding IN CHINA-BEIJING

#### Draft One-Year Proposal (to be extended  based on impact evaluation)

May , 2009– April, 2010

Prepared by:

Dr. Everold Hosein (Ph.D.)

WHO Senior Communication Advisor/Consultant

WHO/WPRO Communication Consultant

in collaboration with  Capital Institute of Pediatrics, Beijing, China

1st Draft: January 26, 2009

Introductory Notes

# Plan Developed in Consultation

This  COMBI (Communication for Behavioural Impact) Plan/Strategy for  increasing the  level of six-months Exclusive Breast Feeding  (EBF6) in China-Beijing was commissioned by the World Health Organization/Western Pacific Region (WPRO)in collaboration with the Ministry of Health/China and the Capital Institute of Pediatrics in Beijing  as part of a specially-funded programme to increase levels of 6-months exclusive breastfeeding in selected countries in WHO’s Western Pacific Region. The COMBI Plan was developed in the course of a 10-day field mission to Beijing in  November, 2008. It is based on consultations with various levels of staff of the Ministry of Health (MOH), the Beijing Municipal Health Bureau (BHB),the Capital Pediatrics Institute (CPI), staff of UNICEF/China and WHO/China, and various non-governmental organizations working on breast feeding in China. A one week COMBI workshop was held for about 23 participants from the different institutions dealing with breast-feeding: WHO/China, UNICEF/China, Ministry of Health Maternal and Child Health Department, China Preventive Medicine Association and Society of Child Health, Child Health Institute/QiLu Children Hospital, China Center for Disease Control--Nutrition and Food Hygiene Office; CDC Food Fortified Office; CDC National Center for Maternal and Child Health, Haidan District Working Committee for Women and Children; Japan-China Friendly Hospital Department of Disease Prevention; GAIN; Capital Institute of Pediatrics; MCH Institute of Huairou District; China Consumers Association/Department of Marketing Monitoring, Community Health Center of Miaocheng; a Breastfeeding website; People’s Hospital  of Huariou District. Three working groups of the participants presented at the end of the week three draft COMBI strategies for increasing levels of  EBF6.  Ideas presented in those reports informed the design of this COMBI Plan. Three-days of field work was carried out and involved visits to hospitals in two districts in Beijing area, and home visits to new mothers.  A full list of people met and the programme of visits are available from the Child Institute of  Pediatrics (CIP). (Note of appreciation: One wishes to thank the staff of CIP, and especially Prof. Dai Yaohua and her associates -- special mention must be made of Dr. Chen Li -- for their extraordinary support in this exercise.)

Various background documents were reviewed as part of the planning exercise. These included: Technical Report  on Nutrition Improvement Programme of Infant and Young Child in Western Areas in China (2008); Technical Report on Monitoring Compliance of the International Code if Marketing of Breast Milk Substitutes in China (2003); and various WHO documents on exclusive breast-feeding.

This draft is to be seen as the first of three rounds of developing a COMBI Plan, in the design approach taken by WHO. This first draft is just that: a first draft. It should be widely shared among colleagues in the various relevant MOH department/programmes/centres involved in the subject matter. A second draft should emerge which takes into consideration the various responses from those who have reviewed the document. We then suggest a meeting hosted by the MOH/BHB/CIP,  WHO and  UNICEF and other interested parties at which further discussion of the second draft takes place, and a detailed work plan is finalised indicating who will do what when. The third version to emerge is the “final” document but which itself remains subject to change depending on new circumstances.

# Presumed Context

## This plan is presented in a context which presumes that the reader is familiar with the breast-feeding situation in China . Relevant information will be provided along the way as we proceed with the COMBI Plan design.  The COMBI Plan focuses on the Beijing area (as suggested by the CIP), to be later rolled out to other provinces as appropriate. There are about 150,000 births per year in the Beijing area. According to the 2005 Food and Nutrition Surveillance Report, nationally only about 40% of mothers carry out “almost exclusive breastfeeding” for 6 months. “Almost exclusive breastfeeding” refers to breast feeding plus intermittent addition of water.  The national percentage for “almost exclusive breast-feeding for 4 months” is a bit higher at about 54%. Breast feeding (regardless of whether exclusive or not)  as a practice is quite widespread: about 90% of mothers breastfeeding up to four months, about 88 % up to 6 months, about 75% up to 12 months and 50% for up to two years

## THE  SIX-MONTHS EXCLUSIVE BREAST FEEDING COMBI PLAN FOR CHINA-BEIJING (2008/2009)

1. Overall Goal

To improve child survival rates and enhance the development of children in China by increasing the proportion of mothers who exclusively breast-feed their new born for six months, as part of the National Programme for Child Development in China (2001-2010)

2. Specific Behavioural Objective (SBO):

To have 80% (120,000 women) of all women giving birth in Beijing/China during the 12 month period of May 2009 and April 2010 (projected to be 150,000 women giving birth) “exclusively breast feed” their baby for a period of six months from within one hour of birth to the end of the first six months, meaning that they feed the baby nothing else but breast milk, not even water, no other liquids, and no other food but breast milk. This behaviour, for the moment, will be referred to as EB6 Behaviour. It will be later re-branded.

  - Commentary: This section will explain why a behavioural focus to the communication plan and why the specific behavioural objective identified above was selected. The section below presumes that the reader has a prior understanding of the link between exclusive breast-feeding for six months and child survival/child development, as expressed in various WHO and UNICEF documents.

  - Focus: Behavioural, Not Only  Increasing Awareness or  Shaping Public Opinion or Changing Attitudes: The essential first step in designing any COMBI (Communication for Behavioural Impact) Programme, as developed at New York University with WHO, UNICEF and UNFPA inputs, is determining the specific desired  behavioural result(s) or objectives (SBOs). A COMBI planning principle/mantra informs this step:

Do nothing…..make no T-shirts, no posters, no pamphlets, no videos….do

nothing, until there is a clear, sharp sense of  intended behavioural outcomes.

  - Ultimately, what all our health communication programmes are directed at is having behavioural impact. In dealing with exclusive breast-feeding,  health communication work in the final analysis is dedicated to having impact on people’s behaviours with regard to breast-feeding in the first six months of an infant’s life. It does not wish only to increase awareness and having people just understand the importance of  breast-feeding or exclusive breast-feeding vis-à-vis child survival and development. In the long run, what matters is that people are taking action, are carrying out those recommended specific breast-feeding practices . Increasing awareness and educating people about breast-feeding and its benefits remain the foundation for prompting action/behaviour; but it is widely recognised that being aware and educated about a particular behaviour does not ensure adoption of that behaviour. So beyond the educational goals of this COMBI programme, there are intended specific behavioural objectives; and to achieve those objectives would require specially designed strategic communication programmes dedicated to behavioural impact, and not just increasing awareness and understanding. Hence WPRO’s  and the Ministry of Health/China desire to apply the COMBI methodology to the behavioural end-goals in dealing with breast-feeding behaviour in China.

  - This brings us back to the COMBI Mantra calling for sharp specification of intended behavioural outcomes before any communication materials are produced or messages designed, etc. Having a clear sense of the specific, precise  behavioural results desired is the dominant initial focus of the COMBI methodology and provides the basis from which to work backwards in determining what communication actions would contribute to the desired behavioural outcomes.  The singular focus is behavioural.

  - There is an old-fashioned view that one can get the desired actions/behaviours if only people would be properly  “informed and educated” about the recommended behaviours and their underlying rationale.  But in general, increasing awareness/knowledge about anything is a relatively simple and easy task. With sufficient funds one can have everyone in  China fully informed about  key breast-feeding issues and educated about recommended breast-feeding behaviours in about six weeks. In fact in China some level of breast-feeding is carried out by almost every mother; according to the 2005 Food and Nutrition Survey, about 90% of mothers carry out some level of breast-feeding during the first four months of their babies’ lives.  The benefits of breast-feeding have been already widely promoted. And it seems that people are aware of the recommendation regarding exclusive breast-feeding. Yet the level of practice is still below what is desirable; only 40% carry-out some version of exclusive breast feeding for the first six months of their baby’s life, and about 54%  carry-out some version of exclusive breast-feeding for the first four months. With regard to this latter figure, one must see it relation to the widespread knowledge about 4-months exclusive breast-feeding which has been extensively promoted in China. One acknowledges that it was only in 2006/2007 that the decision was made to recommend to the public exclusive breast-feeding for 6 months and this partly explains the lower figure of some kind of exclusive breast-feeding for 6 months.

  - Again, one would argue that it would be relatively easy to have everyone know about the new recommendation on 6-months exclusive breast-feeding. The real demanding challenge is getting people to act on the basis of what they know. And one repeats for emphasis:  it is now widely understood that an informed and educated individual is not necessarily a behaviourally responsive individual. Behavioural responses go beyond knowing what to do. The cliché remains true: knowing what to do and doing it are two different things.

  - COMBI focuses on the “doing” which is our ultimate goal in any case. COMBI sees “increasing awareness/knowledge” as an essential, necessary step but not sufficient for prompting desired behavioural outcomes.  . And to advance work only on increasing awareness/knowledge without attention to specific behavioural results is to use resources poorly. Hence this singular focus on the SBO.

  - Too Many Behavioural Objectives: The work of the Ministry of Health/China (MOH) on infant and young child feeding and in establishing Baby Friendly Hospitals is awash with a multitude of desired behavioural outcomes, including a number of behavioural objectives just with regard to breast-feeding. There is a temptation to pursue too many feeding-related behavioural objectives  with regard to an infant. If one is about to embark on a breast-feeding campaign, some would think why not add to that some “young-child feeding” behaviours as well, since we are engaging the same mother and the child.  The problem here is that we then overwhelm the mother with information and not much sticks from a knowledge or behavioural point of view .

  - But even with just breast-feeding, one is faced with a variety of behavioural objectives: the general “breast-feed your child”; start breastfeeding within an hour after birth; ensure the baby attaches properly to the nipple early in breast-feeding;  give only breast milk and not give anything else, not even a drop of water;  breast-feed exclusively for four months (the old message circulated in China); breast-feed exclusively for six months (the new message); give no other foods while breast-feeding during the first six months; do not combine breast-feeding with infant formula in the fist six months; refuse gifts from the infant formula companies; have no promotion of infant formula anywhere in the hospital; all nurses and doctors should not accept any gifts from infant formula companies; no medical staff should be handing out sample of infant formula to mothers who have just given birth; report any attempt by the infant formula companies to promote or distribute samples of infant formula;  during the first six months, if you are at work, express breast milk and put in a refrigerator for taking home later; breast-feed on demand.

  - Each behaviour listed above or hinted at has its own unique rationale and actions. The communication strategy for each will need to be different, although one can envisage a judicious blending of a relatively few closely connected behaviours.  But one can’t arrive at a communication strategy unless one has a clear sense of exactly what behaviour to request and one understands that recommended behaviour from the perspective of the consumer.

  - If we go to consumers all at once with, say, six  recommended behaviours, we will simply overwhelm them and they are likely to turn away from any attempt to engage them. One also recognises that people can recall at the most only three messages from any single presentation. To present consumers with six behaviours and their rationale is to court disaster.

  - It is not wise (and in any case not possible) to have a single COMBI programme directed at a wide and wild variety of behavioural results. Were one to do so, one would end up like a butterfly, flitting from one flower to another, being very busy, but not accomplishing a lot in terms of behavioural impact. The COMBI technical advice is to limit one’s focus over a specific period of time with a COMBI Plan focusing on a single major behaviour (with perhaps three linked micro-behaviours).

  - Limiting the Behavioural Focus:  This COMBI Plan focuses on one behavioural objective as the basis for a major effort in Beijing  to increase the level of exclusive six-month breast feeding. As already explained, to engage mothers and the health community with a multiplicity of behavioural requests would confound them. We need to have a singular behavioural objective around which mothers, families, the community, and health staff can come together for joint action.

  - China has considerable past experience in promoting the benefits of breast-feeding, and the more specific behaviour of exclusive breast-feeding for four months.  As mentioned earlier, in terms of any kind of breast-feeding, the national average breast-feeding rate in the first four months of birth is 90%, and  about the same for the first six months. Success has been modest, however, when it comes to exclusive breast feeding. At the time of writing,  no figures for “true” exclusive breast-feeding for either 4 months or 6 months were available though there was a figure of about 15% of true EB4 in selected cities;  there was data for “almost exclusive breast feeding” which means that  some other liquid such as water  was given to the infant in addition to breast milk.  The case for proper exclusive breast feeding for the first six months (meaning nothing but breast milk) is medically substantial and the MOH clearly wishes to achieve the target of  85% exclusive breast-feeding for the first six months. Hence the singular focus in this COMBI Plan on the one behavioural  objective of getting every mother in Beijing giving birth to give only breast milk and nothing else (not even water) to the baby for the fist six months of his/her life. While there are other related behaviours, the behavioural result which will be measured is that of proper exclusive breast feeding in the first six months and we will refer to this as: EB6 Behaviour.

  - One could focus solely on the behaviour of  attaching the baby to the nipple within the first hour of birth. There is the argument if this can be accomplished effectively then it sets up the basis for continued breast-feeding. There is merit in this argument but one is not sure that simply getting that attachment in the first hour assures one of proper exclusive breast-feeding for the next six months. This within-one-hour attachment is a key step in the process of getting EB6 Behaviour  but one will need a significantly different communication plan for getting and sustaining EB6 Behaviour compared to just getting attachment within the first hour. The “attachment within one hour” behaviour will be treated as a micro behaviour on the way to proper exclusive breastfeeding; in fact, the definition of EB6  includes the early within-one-hour of birth start of breast-feeding.

  - It was felt that one should begin the COMBI Programme in Beijing with its large urban population rather than try to cover all of China with one COMBI Plan. The Beijing experience will inform plan for rolling out this approach in other provinces and cities. It would be enough of a challenge in the first instance to take on  the entire city of Beijing  with its 12 million population and almost 1 million women in peak child-bearing age (20-29 years of age). In addition, there has been a slow decline in almost exclusive breast-feeding rates in urban areas over the years. The rate of “almost exclusive breast feeding for four months”  in urban areas is lower than in general rural areas and  fell slightly from 55% in 2000 to 52% in 2005.

  - In a 12 month period in Beijing there are about 150,000 births. If past urban averages hold, we should be able to get  about  80% carrying out some level of breast-feeding in the first six months, even if water , other liquids or solids are added during that six month period.  In urban areas, the “almost exclusive breast feeding rate” is about 33%, and the proper EB6 rate is about 16% for urban areas, according to one report. Given these figures, one is confident that with a strategically designed COMBI Plan, one can aim for getting 80% to carry out proper exclusive breast-feeding for six months. For most mothers, breast-feeding is an acceptable behaviour; the challenge is trying to get it to be the exclusive behaviour for 6 months. If 80% are already doing some breast-feeding for the first  6 six months, then we should attempt to drop all other liquids and food and just stick to EB6.

  - After much consideration, the behavioural objective recommended became that of trying to have 80% (120,000 women) of all women giving birth in Beijing/China during the 12 month period of May 2009 and April 2010 (projected to be a total of  150,000 women giving birth) “exclusively breast feed” their baby for a period of six months from within one hour of birth to the end of the first six months and feed the baby nothing else but breast milk, not even water, no infant formula and no other food but breast milk (EB6 Behaviour.)

  - The COMBI Plan presented in this document will focus exclusively on this behavioural objective of EB6. In the “Strategy” section below we will explore how we will go about trying to achieve this specific behavioural objective (SBO).

3. Strategy

A general overview of the COMBI Strategy is presented in this section with various interventions typed in “bold” font to provide a sense of the mix of interventions. Further specification of the communication actions suggested will follow in the subsequent section and a short summary of the interventions will be presented at the end of Section 4.

  - The COMBI strategy here proposed is behaviourally driven: it focuses on that ultimate desired result of 80% of women giving birth in Beijing in a 12 month period feeding their new born breast milk and only breast milk for a full period of six months after birth, beginning within one hour of birth of the new baby. The strategy presented below is based on some understanding of those factors which would hinder this behaviour and those factors which would facilitate it.

  - The COMBI strategy for the above behaviour needs to be informed by the available data and other insights as to why people would carry out the recommended behaviour, or not. In the process we will be repeating some data earlier presented.

  - A review of field observations and conversations in China-Beijing suggests that individuals will follow-through with the recommended behaviour if in their cost vs. value calculation they conclude that it is worth it to invest the effort and bear the “cost” in carrying out the behaviour in relation to the value of what they receive in return, and in relation to what other “competition” there is in the environment or “market place.”

  - For most people, they see value in giving their baby breast milk; about 90% feed their baby breast milk for as long  as six months, with 75 % continuing to offer some breast milk until 12 months old. These are national estimates; the figures are higher for rural areas compared to  urban areas. There seems to be no particular distaste for breast feeding, or a massive inability to breast-feed.

  - For years, the MOH has promoted exclusive breast feeding for four months after birth. And most of the public know about this recommendation. We do not have specific data from the 2005 nutrition survey regarding proper exclusive breast feeding. One suspects that it is low.  But the data for “almost exclusive breast feeding for four months” (EB4) in urban areas suggest that about half of mothers do carry out this behaviour. This is impressive. In 2007 the MOH began promoting the new WHO recommendation of  exclusive breast feeding for 6 months (EB6) but the 2005 levels for that is a low 33% for urban areas. It seems that a significant number of mothers are able to do EB4 but not continue on to EB6 .

  - Two questions need to be explored here. Why do the other half not even carry out EB4 ? And if you could do EB4 , why not extend by two months to EB6 ?  Let’s look at the first question.

  - The reasons are myriad: some (though a small proportion as reported) simply can’t get the baby to attach to the nipple; some very early on feel that the baby is not getting enough milk even when there is much milk in the breast; some feel that they are not producing enough milk and lack the confidence to that they can breast-feed; some are disgusted by the colour, texture, smell of the first milk on the first day (colostrum), do not know of its health value,  do not think the baby should be having that milk, and so don’t bother with attaching the baby to the nipple soon after birth and this complicates attachment later; some do not know that they can demand the baby be attached to the nipple within the first hour of birth; some are too tired after birth to bother with the demands of early attachment; some feel that the baby needs  water because he/she is crying and therefore he /she is thirsty,  and also it is a way to clear/clean the mouth after breast feeding;  some have to go to work very soon after birth and breast feeding becomes inconvenient; some can’t be bothered by the inconvenience of expressing milk while at work; some are seduced by the promotion of infant formula and feel that this is the modern/upper income approach and more convenient, and part of this seduction is carried out by health staff who on the side promote infant formula in return for a commission from the infant formula companies; some feel that the baby needs to start eating some solids before the end of four months so that  they are accustomed to solids before breast feeding suddenly stops at 4 months; some do not see the value of EB4 for themselves or their babies regardless of time and effort involved in breast-feeding; some fear the loss of shape of their breast from exclusive breast feeding; some experience painful nipples and don’t know how to solve that problem and so give up on breast-feeding after starting; some do not know of the cancer prevention benefit of breast feeding for the mother, and the range of benefits for the baby. All of the above reflect some dimension of the mother’s calculation of cost involved (time, effort) in relation to perception of value for her or the baby derived from EB4 .

  - It is not clear which of the above are the dominant factors which constrain EB4 . Expert colleagues suggest that the sense that the baby is not getting enough milk is a major factor. And for a significant number, the appearance and smell of the early milk is a major issue.

  - And yet for perhaps about 15% of mothers they see the value of proper EB4 in harmony with the costs involved. And an even higher portion, up to about a third, see its value but cannot help but give their baby some water or other liquid, especially if the baby is crying (which is then interpreted to mean the baby is thirsty.)

  - When it comes to the question of why would the 15% or so who do EB4 not continue on for another two months, one answer is the simple fact that people may not know of the recommendation for EB6  and the value argument for it. But even if they know, there are still many constraints to continuing for the next two months, some of them similar to why EB4 is not accepted. Even when they get to know about the EB6 recommendation, they may not be persuaded that there is value for the child or the mother beyond the 4 months, that 4 months is good enough and it is what the MOH has been promoting.  Some would argue that at 4 months it is time to prepare the child for solids. Some only have four months of leave from work and so on return to work they have to give up on breast-feeding and find expressing milk inconvenient.   For some after 4 months of exclusive breast-feeding, they think the “convenience” of formula is attractive. Some fear loss of shape of their breast if they continue for yet another two months. Some feel that by four months the baby definitely needs some water or other liquids.

  - For that one –third who carry out “almost EB6”, it would seem that they do not accept the argument that the baby does not need anything else and that they see value in giving the baby some other liquid like water in addition to breast-milk. This might be the easiest market segment to engage in re-examining  the merits of absolutely nothing else but breast-milk.

  - There are so many different explanations for mothers not accepting the proper exclusive breast-feeding recommendation, either for 4 months or 6 months. One would need to deal with each mother in her unique circumstances and state of mind regarding EB4  or EB6. This would call for intimate personal engagement of each mother in their circumstances at home. But it also suggest that this personal engagement can be started during the pre-natal visits to heath centers and also at the Mother’s Classes which prepares pregnant women for delivery and post natal care.

  - Much of the literature distributed by the MOH  in the health services regarding breast-feeding focuses on the benefits of breast-milk and not necessarily the benefits of exclusive breast feeding (with no water provided) for 4 months or 6 months. Given that almost everyone already acknowledges the value of breast milk, what now needs to be stressed the is the exclusive breast feeding behaviour, with no water or liquids added, and the recommended duration of 6 months.

  - A key challenge is going to be making the case for 6 months EB vs four months as has been promoted these past many years. Why does the extra two months of EB make such a difference, a mother will want to know. Even for health staff, this case will have to be made. It is reported that many doctors in China do not accept the arguments for the extra two months of EB. If we can’t succeed in making the case to our colleagues in the health system, it does not bode well for reaching out to the larger community with an argument for the 2 month extension of EB.

  - Much has been made of the importance of attaching the baby to the nipple at least within one hour after birth. This enables the early start of breast feeding with the important benefits accrued form the early milk/colostrum. One reason given for getting this early attachment is that it greatly facilitates successful breast feeding. One wonders, however, whether any of the 90% who do some kind of breast-feeding for quite a while suffered any  consequences in terms of breast-feeding capability because they did not do the early attachment bit. It seems that one can develop the breast feeding capability even if one did not have the early attachment. Of course, the major reason for that early attachment has to do with the critical health benefits of colostrum within the first few days of birth. However, if breast feeding does not start early (within one hour or so after birth) and in the interim water or some other liquid is given to the baby, then immediately  EB6has been denied the baby.

  - It would seem that  we need to treat the start of breast feeding as soon as possible after birth, preferably within an hour, as a key defining component of EB6 .  The reasons why mothers may not want this early attachment are also many: as mentioned, they find the colour and smell of the early milk disgusting and  do not want to give that to their baby; they do not know of the benefits and value of early milk/colostrum; they are weary after birth and do not want to face the task of attachment; health staff may not bring the baby to the mother within the first hour after birth and proceed to give the baby water; the mother may not know she can demand that the baby be brought to her within an hour after birth. And so we will need to treat the attachment within-an-hour issue as part of the process of getting EB6.  The case for EB6 is a case for breast-feeding and breast-feeding only (with no other liquids or solids) from the start of the baby’s life (within one hour of birth) to the end of six months.

  - We eventually need to arrive at a set of “Communication Objectives”  or “Intended Communication Effects” which, if achieved, will get us the behavioural result. These communication objectives would set out the costs vs value relationship of carrying out the recommended behaviour and offer the key messages one would need to engage a mother to consider and deliberate over.

  - The costs vs value calculation for the recommended behaviour will need to be carefully attended to in the communication strategy. (As earlier mentioned, all behaviour is chosen following an individual’s calculation of the cost vs value, arriving at the conclusion (from his or her perspective that the costs seem in harmony with promised value. And we will need to address the cost vs value calculation in relation to what alternatives or competitors there are. As they say in the business world, you do not know what something really cost until you have seen the alternative. In the case of  EB6, the competitor is clear: give a little water, start solids earlier, and then there is Infant Formula!)

  - The messages will need to address both the Head (logic) and Heart (emotional) dimension of the Cost vs Value calculation. On the value side, we would need to point out the value to both the baby and the mother. Usually we present breast-feeding as being advantageous for the child with all the noted health benefits, but we rarely speak of the value to the mother, which may be more emotional than medical or physical.

  - In addition, we need to think of modest incentives (a small gift of cosmetics, soap, a baby’s bib, a T-shirt, or a toy for the baby, etc) to be promised and given (as part of the communication effort) to every mother as they continue with EB6. These gifts could be  given out after the first month, then after the 3rd month, and then at the start of  the 6th month. A modest incentive offers a psychological way of “reducing” the cost burden and also giving a little extra value to the recommended behaviour. It is also a way of extending praise to the mother, boosting her self-esteem.

  - The recommended behaviour will also need to be re-branded; branding also adds perceived value to a behaviour or product. The brand of “breast milk” is a bit stale. It has been massively promoted in China these many years. It has become an easy message/brand to tune out. One would like to suggest a re-branding of breast-milk to be called now : MNM (Mother’s Natural Milk). The acronym may have a rhythmic sound in English and we will need to seek a version in Chinese. In this COMBI Plan we will use the MNM acronym in the following form MNM6  to indicate exclusive breast-feeding for the first six months. The related theme could be: “Your baby has lived wonderfully within you these past 9 months and was internally fed with your natural nutrients; and now she/he is out in the world but not yet ready for the world. Your baby yearns for  the natural within you…and wants that continued bodily connection with you Your baby wants and loves Mother’s  Natural Milk, MNM, nothing artificial.”

  - The messages will need to address the key constraints set out earlier but with a special emphasis on why the MOH/BHB is recommending EB6 rather than the old message of EB4 .

  - The discussion above offers the broad outline of what we can offer individuals in terms of the value of the recommended behaviour in relation to the “cost” involved in carrying it out and in comparison to the “competitors”. In this outline are the themes which will form the basis for engaged communication with a wide variety of people in China-Beijing, both male and female, but with the ultimate focus being on the behaviour of the woman who has just given birth.

  - A woman who has just given birth will carry out the recommended EB6 behaviour if she is:

    - Reminded of the wonderful, remarkable benefits for the growth of the baby and protection from diseases of giving one’s baby only breast milk and nothing else for the first six months after birth, in addition to the wonderful benefits for herself (including cancer prevention);

    - Persuaded that she has the full capability for breast-feeding and that with early orientation before giving birth and early practice right after birth, breast-feeding would be a relatively simple and will become a loving, bonding act between mother and child;

    - Advised that the early start of breast-feeding may be a little challenging but with a bit of  effort and practice it will become the most natural act, and that the challenges can be taken care of (such as painful nipples);

    - Understands that it is natural for a baby to want to be immediately connected to the mother after 9 months inside and now suddenly out in the world and why for bonding and better care for the child it is important that the baby be bought within one hour of birth to the mother’s chest/breast;

    - Knows that she can make a firm request/demand  that her baby be bought to her within an hour of birth (provided that there are no emergencies) and is urged to make that request if the baby is not brought to her within that time period;

    - Understand that the first milk (colostrum) on that first day is vitally important for the baby given all the protective and disease prevention factors involved in the baby being fed with that first milk and that the earlier the baby gets it the better;

    - Understands that the baby would love to be taking in that first milk as the first reconnection to the mother  outside after 9 months in-side, regardless of the colour and the smell and the texture of that first milk;

    - Recognises the joyous feeling of bonding when the baby comes to her right after birth, facing this new world  away from the security of the womb but embraced by the security of  loving hands, mother’s beating heart, and oral connection to the breast.

    - Understands that the baby in its early days has a very tiny, tiny stomach and needs only a very little amount to feel filled-up, so that even though the mother may not be producing vast quantities of milk at this stage, the body naturally produces just enough to fill the baby’s very small stomach which is the size of ------- during the first few days;

    - Persuaded that the baby needs  no water during the first six months because breast milk is 80% water and the baby gets all the water it needs from the mother’s breast-milk, and that if the baby is crying, it is not out of thirst but some other reason (such as  wanting more breast milk, or wanting to be changed) ;

    - Understand that filling up the baby’s stomach with water deprives the baby of the nutritious elements of breast milk, that breast milk during the first six months  gives the baby the right amount of water and growth-building nutrition for its small stomach;

    - Believes that water for cleaning the baby’s mouth after breast feeding is not necessary since the baby does that naturally and likes the taste of Mother’s milk lingering in his or her mouth;

    - Appreciates that while the water may be clean for adults, for a new born just out of the womb accustomed for 9 months to the natural liquids of the mother internally to now face the strange chemicals that may be in water is a shock to the system and may even be dangerous for the baby, especially when there is enough water already in breast milk to satisfy the baby’s tiny stomach;

    - Persuaded that at no time in the first months of a baby’s life does he/she need anything else but breast milk—no water, no other liquids, no solids, no infant formula—nothing but breast milk which has everything that a new born needs for the first six months of its life;

    - Feels that it is an act of love to give the baby six months of natural breast milk after the baby has spent nine months inside her body growing on just natural nutrients provided by the mother internally,  and now that the baby is outside, he or she is deserving of  continuing this natural connection with mother via breast-feeding rather than being suddenly shocked with artificial foods for its tender and small stomach during the first six month;

    - Persuaded that while the old message has been exclusive breast feeding for four months, the new research convincingly shows that the benefits of breast feeding can be extended for another two months, and that 6 months is a better age for the baby’s stomach to absorb solid food, that before that the baby’s stomach is still too tender to deal with solids. some have to go to work very soon after birth and breast feeding becomes inconvenient;

    - Convinced that breast-feeding is far more convenient  and easier than giving the baby infant formula (what with all the bottle washing and having to get up to mix formula, plus the costs of formula, plus the fact that it is artificial, not natural and does not have all the nutrients that Mother’s Natural Milk has, etc.)

    - Persuaded that even one has to go to work, that one can take a little time off during the day to express milk  (recognising that this is a burden but a loving burden from a caring mother) to be stored in a refrigerator and that this can be done before going to work, and during work, thus making sure that the only thing the child is fed with for the first six months is only, only breast milk.

    - Knows that there is no need to prepare the child to eat solids during the first six month since the baby’s stomach is not quite ready for solids—it is too tender and small, and that at six months, that is the time to start slowly introducing solids;

    - Believes that exclusive breast feeding for six months has wonderful benefits for the mother herself, including regaining shape after birth and maintaining breast form.

    - Feels that having this exclusive natural connection via breast milk and only breast milk in the first six months with her baby is her most perfect gift to the new born, and that it is worth very effort, every little burden to make it happen, and that her husband and extended family and friends will be so proud of her for this, and that in return she will receive an appreciation gift from the MOH after one month of true exclusive breast-feeding/breast milk feeding, and another gift after the third month, and a third gift at the beginning of the sixth month.

  - As we have mentioned, the above 21  communication themes (“The 21 Things You Need to Know about EB6”) are all part of the cost vs. value calculation which mothers carry out in deciding on  EB6. Sometimes the calculation is not all logical; often emotions play a critical role; and human behaviour in any case remains a daunting mystery – we do the oddest things for strange reasons.

  - While the above-mentioned themes of the cost vs. value calculation will form the content of the “conversations” we need to have with mothers of newborns in China-Beijing as they consider the recommended EB6 behaviour, a favourable cost vs. value calculation, while necessary, is often not sufficient to prompt the desired behavioural response. People may know the right thing to do but still don’t carry it out. People need to be triggered and nudged and encouraged to do what they already have calculated is the “right” thing to do. And some of these triggers can be provided by other family members, neighbours, friends, relatives, co-workers, and other community members. Here too lies the value of modest incentives and branding of the recommended behaviour.

  - Pre-Requisite: There is a pre-requisite for the proposed COMBI Plan which needs to be stated upfront. Before the proposed COMBI Plan is executed, all relevant health staff need to be retrained on the importance and value of MNM6 . The MOH has been promoting “exclusive breast feeding for four months” for many years now. Health staff  were trained quite some time ago. And so too the training regarding the within-one-hour-after-birth-breast-attachment.  Now that the MOH has committed itself to EB6  promotion, it is important that all health staff be re-trained in the new recommendation, taking care to develop the case of why it is worth it to extend exclusive breast feeding to six months. Already some staff members (including doctors) do not accept the arguments for the two month extension. The training should once more emphasise the need for the within-first-hour breast attachment behaviour; and also the absolute no giving of water or any other liquids to the infant right after birth. All staff should be encouraged to always raise the issue of 6-month exclusive breast feeding with a mother with a new born whenever they have to provide health care for the mother or child, and should congratulate and praise the mother for her behaviour, and offer help with any breast-feeding problems. In addition, all health staff should be reminded of the Code against promotion of infant formula by health staff within or outside the health facilities, and the penalties involved. They should be urged to do the best for Chinese babies and the best is to promote MNM6 .As a pre-requisite , therefore, it is recommended that the MOH in collaboration with the CIP conduct a one-day re-training on EB6 for all health staff  in all health facilities in Beijing before the launch of this COMBI Plan.

  - The proposed COMBI Plan focuses on the specific desired behavioural result indicated earlier and consists of an integrated, judicious mix of a variety of communication interventions responsive to the issues raised above.

  - One of the early actions required will be to brand the recommended behaviour. The branding should consist of both a special logo and tag line/phrase. A graphic design firm or advertising agency should be selected to develop this logo/theme through a competition with a fixed monetary prize going to the winner.

    - In English, one possible branding approach could be the following:

Your baby’s first six months:

Nothing but the Very Loving Best!

MNM6

Mother’s Natural Milk

And absolutely nothing else! All your baby needs is right there in MNM6 -Your loving breast milk for intelligence and miraculous growth for your baby. No water, no other liquid, no other food—for the first six months. Just MNM6

Obviously this will need to be done in Chinese and while MNM may not survive translation, some similar re-branding of exclusive breast/breast milk feeding should be conceived.

    - The MOH has had a national breast-feeding programme for many years and has spent substantial time and effort in establishing Baby Friendly health facilities. The MOH has been quite active promoting four months exclusive breast-feeding. And most people seem to know about the recommendation. We suspect, however, that this “brand” has gotten a bit jaded as brands for many commercial products do. But because of this familiarity, people may more easily dismiss any new messages unless they stand out distinctively. The new focus on six months exclusive breast feeding provides a basis for re-engaging the public afresh.  As in the private sector, sometimes one needs to take an old brand of a product, make some modest changes to the product (for example, with Colgate toothpaste,  add a teeth whitener chemical, give it a new “pumped-up” name (such as Colgate Plus--Colgate +) and launch an effort which says we have something even better than the last time with the additional benefit of the teeth whitener. This sort of re-branding is now quite common in WHO and UNICEF where we have found new terms and logos to address old health issues such as malaria, TB, maternal and child health, etc. We need to do something similar to this behavioural recommendation of exclusive breast-feeding for six months (EB6).

    - The behavioural theme/logo should be simple and elegant in design, easy to duplicate and in two colours. The logo need not have any symbolic meaning in relation to exclusive breast-feeding; by constant use it will be become associated with  the recommended behaviour, in the same way the “swoosh” of Nike which has nothing to do with athletic shoes has become associated with that brand of product over the years. Eventually one may wish to just use the logo by itself as a trigger for the recommended behaviour All communication materials, letterheads, folder etc, associated with this COMBI Plan should carry the logo and colours, even when associated with existing logos for the MOH/BHB or CIP. The above logo (MNM6) is merely suggested at this point but will be used henceforth in this document until an approved alternative is agreed upon.

  - The key behavioural theme will then need to be put into some simple form to be used in all media and communication actions. The following is one such attempt and will need to be expressed in appropriate Chinese: “An important public message for women  of Beijing. If you are pregnant now, plan now on how to give nothing but the very best to your baby– from it s first hour and for the next six months. Nothing but MNM6. No water, no other liquids, no food…just your loving MNM6.  It has everything your lovely baby needs…and after 9 months within you, it needs just six months more of exclusive connection to you…you can give that gift to your baby with the love and bonding that comes with MNM6. For intelligence and the best growth, give only MNM6  and nothing more….for the first six months. And at the same time protect yourself from cancer. A loving mother gives only MNM  for the first 6 months” …..

    - We then go on to add in an extended version, and in intimate, effective Chinese points related to the key themes listed in 3.23 above.

  - The above is suggestive of what can be said; basically we want to suggest the recommended behaviour and explain why, in terms of “cost” vs. value, it is worth carrying out the behaviour.

  - The heart of the COMBI Strategy is what the private sector would call direct sale or personal selling: the door-to-door, face-to-face  engagement of the consumer in his or her home. The mass media will also be used and will provide the backdrop for the more personal engagement which takes place between a “personal seller” and a woman. It is widely recognised that the ultimate key to action on a recommended behaviour is in the personal interactions between the consumer and a “seller”. The quality of instantaneous feedback in the personal interaction and the ability to raise questions and have them answered there and then make for a dramatic impact on going from awareness about a recommended behaviour to putting it into practice. It is the personal communication between a pregnant woman or a woman who has just given birth and a MNM6  “personal seller”/advocate ( a relative, neighbour, friend, nurse, doctor, husband) which will help convert knowledge of MNM6  into action. This COMBI Plan will use the concept of personal sellers in two ways: one has to do with door-to-door communication between a volunteer/ “Ambassador” (who has practiced exclusive breast feeding) and a mother with a newborn in the mother’s home in Beijing with regard to the behavioural theme ( a kind of mother-to-mother –MTM - counselling for MNM), and the other has to do with the face-to-face interaction  as conducted by health staff at each health centre during pre-natal care, care at and right after delivery, and neo-natal and post-natal care.

    - Firstly, by a newly-branded core of some 1,500  volunteers to be called Baby Love Ambassadors (BLAs), each of whom will be asked to “work” with 100 mothers who have just given birth and encourage them to carry out EB6 / MNM6 . Each volunteer will be assigned about 100 mothers who have just given birth and will be asked to visit that mother once per week to discuss with the mother and the family MNM6  and other related child care and child feeding issues as the child gets older, until the child reaches the age of two. Each visit could last from 15- 30 minutes, and sometimes shorter if there are no special issues to discuss. With these 1,500 BLAs we should be able to cover all 150,000 births in Beijing per year. Each BLA will be assigned a specific area and will be notified when a mother has just given birth and is scheduled to arrive home. At each home, the BLA will hand out on the first visit a single-page, two-sided  MNM6 Advisory Sheet (which could also be called the “21 Things You Should Know about EB6/MNM6” as covered in 3.23 above.) This sheet will cover the behavioural theme expressed above, in a nicely laid out presentation. On one side is the basic behavioural message and rationale, with the key behavioural theme mentioned at least three times, covering the key issues as in 3.23 above, especially the rationale for no water, no liquid, no other foods during the first six months.  These themes are extended to the other side. The latter half of the other side would have a “calendar” of sorts for a six month period, broken up into 183 small boxes (each box representing a day, and so covering 6 months), with a separation between each month. The mother is asked to tick off each box each day after she has completed true MNM6  for that day. At the end of the first month , the BLA checks this sheet and if all boxes are ticked off for that month, the BLA affixes a  MNM6  Gold Star sticker to that month’s section and gives the mother and the baby a small gift (the nature of the gift to be determined later—chocolate, a small child-proof toy, vitamins for the mother, soap, an MNM6 baby bib??). This is repeated at the end of the 3rd month, and the start of the 6th month. The BLA will congratulate the mother each time she gets a Gold Star sticker and say something to the effect of what a wonderful gift the mother is giving her baby.

    - At the first home visit, the BLA will go over the basic behavioural theme of the sheet as she hands over the sheet and tries to emphasise the key MNM6 behaviour recommended at least three times in the sheet. The BLA will focus on the MNM6  recommendation and will pay special attention to the cost/value decision-making process.  And they will point out the small special incentive the mother and child will get from time to time if the MNM6  behaviour is practiced faithfully, with no water or other liquid or other food given. The BLA should urge other family members (wives, husbands, in-laws) and other care givers at home at the time to read the Advisory Sheet The BLA also asks if they have any questions and sensitively responds to these questions.

    - The name “Baby Love Ambassador” is suggested rather than “Volunteer” or Breast-Feeding Advocate or other similar term. The term “Ambassador” provides a bit of status. And “Baby Love”: is intended to reflect the overall theme of their volunteer work…love of baby and giving the baby love. Baby Love sounds less health/medical related and brings in the emotional dimension of child care and of MNM6/EB6…thus addressing the mother’s need/want/desire related to the idea of “love” for the child rather than only the technical are of worry about child survival. BLAs will be encouraged to go beyond the health rationales and invoke the theme of “loving care. The first part of their work will focus on MNM6/EB6 but as time goes on these BLAs could focus on other dimension of child care and development, including the many other behaviours related to immunisation, and Infant and Young Child Feeding practices.

    - The selection and training of the BLAs is of critical importance . There is already a network of volunteers in the All Women’s Federation and in the Neighbourhood Committees at the various administrative levels of the Beijing Municipality (counties, townships, villages). There are also community health workers and teachers who may be willing to serve as BLAs. The Women’s Federation and Neighbourhood Committees should be invited to participate in this COMBI programme and should be asked to identify the 1,500 BLAs based on the following criteria: the prospective BLA should have practiced MNM6/EB6 with her baby; should be comfortable with making home visits; should have good empathetic communication/listening skills; should be literate.

    - Each BLA will be given a large BLA badge and special coloured light-cotton jacket/vest to wear on their home visits. In addition to the BLA badge, the BLA will also wear an additional MNM6 badge when making home visits related to exclusive breast-feeding. Each  BLA should receive a personally addressed memo from the Mayor of Beijing  (or other senior official) inviting them to be a BLA and requesting their keen participation in the home visit programme and thanking them for their contribution to child health and development.

    - Each BLA in groups of 20-25 will receive a two-day non-residential training by an appropriate senior staff member from the nearest MCH hospital or General Hospital or Township Hospital  who is a specialist in MNM6/EB6  and who will serve as their Mentor/Trainer and informal supervisor. The training should cover the key elements of the MNM6/EB6 Information Sheet – “21 Things You should Know about MNM6/EB6”.  One day should be spent on all the technical information they need to be aware of, especially the 21 Things You Should Know…..emphasizing  with explanations that all the baby needs for six months is breast milk with no water added or other liquids or foods; and the second spent in role playing sessions in which each  BLA plays the role of  a mother with a newborn and each plays the role of Ambassador going through the process of engaging the mother  in the  discussion of the MNM6/EB6 behaviour. During the technical session, it is important that the BLAs be given advice on how to counsel a woman who is having difficulty with breast-feeding (such as having painful nipples or little milk flow), with specific suggestions being offered with regard to specific problems likely to be encountered. Also the BLAs should also be trained on how to advise a mother on expressing milk. The communication role-playing part of the training should stress active listening skills and exploration of the cost vs value analaysis from the mother’s perspective. The BLAs should also learn to focus on both the technical and emotional dimensions of breast-feeding.

    - The BLAs will not be paid but they will be rewarded in various ways  and provided with on-going motivational social opportunities for sharing experiences.  Three quarterly gatherings of the BLAs  (in groups of  50) will be held at various County/District locations. At these gatherings they will be thanked by the most senior Municipality Health officer available at that level, provided with a simple meal (tea and cakes?)  and given gifts donated by the private sector through a Business Partnership for Baby Love  to be established. They will also have an opportunity to share their experiences with their colleagues. In the last quarter of the first year, a Thank You Ceremony will be held at the country/district level for all BLAs and associated  health staff (such as the Mentors )at which a simple meal will be served, a Certificate of Appreciation signed by the  Mayor handed to each, private sector-secured gifts given to each, and a Lucky Draw Prize given to ten lucky BLA and her Mentor.  (Perhaps the Lucky Draw could be done per County/District.) The Prize could be an all expenses-paid three-day weekend trip to a tourist resort donated by a hotel and airline company. The certificates and thank-you event and lucky prizes are small ways of expressing appreciation and motivating  these committed BLAs and health staff.

    - Secondly, by way of enhancement of the “Personal Selling” experience between a pregnant women  and health staff  during her prenatal visits, her attendance to Mothers’ Class, at the time of birth, and during that period the mother is in the hospital/health facility right after birth, and during  neo-natal/post-natal visits..

    - These several occasions of contact between the pregnant woman/mother and health staff are critical moments of interaction during which the MNM6/EB6 case should be “sold” by person-to-person interaction:.

      - All health staff working in pre-natal, delivery, and post-natal care will be given a special MNM6/EB6  badge to wear at all times.

      - At each pre-natal visit the pregnant woman should receive a small token MNM6/EB6  gift (donated by the Business Partnership) together with an information item related to MNM6/EB6 , such as: The Advisory Sheet (21 Things You Need to Know…) to be given out at the first visit, the third visit and the last visit before birth, and reviewed and quickly discussed each time; a small information  card (Information card #1) with possible names for children (boys and girls)  but the front side focusing on  the theme of MNM6/EB6  : No water, no liquids, no foods, with simple explanations of why just MNM6/EB6  is enough for the first six months and nothing else is needed; another information card (Information Card #2) on MNM6/EB6  showing the size of a baby’s stomach after birth, pointing out that the baby needs very little at this point to feel full, that the fist milk is fantastic for the baby and why (even though the colour and smell may not be attractive to adults) the baby would love it as the fist natural thing to have after being in the mother’s womb for 9 months, and so the mother must make sure to ask for that baby soon after birth, like an hour, and try attaching the baby to the nipple with the help of a nurse; an Invitation Card to attend a special session of the Mothers Class on exclusive breast feeding to be redeemed at the end of the class for a special gift (e.g. sample cosmetics?); and a MNM6/EB6  Request Card with the woman’s name on it to be given to the nurse/doctor at the time of delivery requesting that within one hour of birth the mother wishes to have the baby on its chest and help from the nurse to have the baby attached to the nipple so that the baby can have the benefits of the early milk (colostrum), plus a request that no water or other liquids be given to the baby unless there is an emergency. This last card should have a box to be ticked and signed by the woman if the request is met by the doctor/nurse after delivery. As mentioned, at the first, third and final visit before giving birth, the pregnant woman receives the information sheet about the 21 Things You Should Know…At each of the other prenatal visit, the pregnant woman/mother should receive one of the cards described above; and at the last prenatal visit, together with the information, sheet she receives the MNM6/EB6  Request Card and advised to give that card to the nurse/doctor when she goes in for delivery. The use of this last Request Card will be described below.

      - Each prospective mother should be invited to a special Mothers’ Class session on MNM6/EB6 . At the appropriate  prenatal visit, the mother will receive the invitation card as described above to be used for redemption after the class for a special gift. At this special class on MNM6/EB6 , a  14-minute video is shown covering the “21 Things You Should Know…”, grouped in threes, with a question and answer/discussion session after each three. The class should emphasise the benefits of exclusive breast-feeding, why no additional water/liquid food is needed, why six months rather than  just 4 months why mother should insist on getting the baby within an hour after birth, why mothers should worry about the amount the baby takes in—noting the size of the baby’s stomach soon after birth, the fantastic benefits of colostrums despite its smell and appearance. At the end of the session mothers can redeem their invitation cards for the small gift.

      - At the birthing/delivery moment, the doctor/nurse should ask the mother on her arrival if she has the MNM6/EB6  Request Card mentioned above. The doctor/nurse should take the Request Card and enter their names in addition to the mother’s name if it is not already there. Within one hour after birth the doctor/nurse brings the baby to the mother, helping the mother with attaching the baby to the nipple for the first feed of colostrum, and advising the mother that no water or other liquids has been given to the infant. After the baby has been taken away after this first feed, the mother is asked to tick the box indicating that the Request was met and to sign the card. The card  should then be sent to --------??? (to be determined). Every quarter there will be a Lucky Draw of these cards with the ticked box  and signature and special donated prizes will be given to 10 lucky winners each time, the winners being both the mother and the doctor/nurse in attendance. (The prizes are to be decided upon later and in consultation with the Business Partnership).

      - Also at this time just after delivery and before the mother departs for home, the mother is given another copy of the Information Sheet (“21 Things…….”)  but on the back on the “calendar” an MNM Gold Star sticker is appended next to the first box, indicating that MNM was begun successfully on the first day. The nurse/doctor should congratulate the mother and stress what a wonderful gift the mother has given the baby. The nurse/doctor should also remind the mother of the key things in the  Information Sheet (such as no water/liquid/foods for the next six months, that MNM has it all including enough water and all the nutrients for a bright and well developed baby. The mother should be reminded to give the Information Sheet with the MNM6/EB6  Gold Star sticker to the visiting nurse/doctor when she returns home to indicate that MNM6/EB6  begun successfully.

      - At each Neonatal and Post-natal encounter with the mother during the first six months, attending health staff should always  remember to remind the mother of the value of  MNM6/EB6  congratulate the mother on her breast-feeding practice. Health staff should also ask if there are any problems/challenges and should help the mother resolve these.

      - The above mentioned health staff should receive a special memorandum from the BHB advising them of the above duties/task with a request to each supervisor that these items be thoroughly discussed and rehearsed.

      - Each of the above mentioned health staff should receive a Thank You letter from the BHB at the end of the year and should be invited to attend the Thank You Ceremony for the BLAs, described earlier

  - This “personal selling” will be supported by a media-based public relations campaign comprising sustained press activity during the year, short 15 sec “filler” radio announcements to be used by radio disc jockeys (DJs)/announcers in between musical pieces on radio, thematic insertions in existing radio/TV local drama serials, and radio and television discussion/chat shows with telephone call-in and done before live audiences.

    - The press activities will consist of a MNM6/EB6  launch press conference, followed by three press conferences during the course of the year, covering key aspects of the behavioural messages and rationale and any progress results. The launch press conference should be hosted by the highest possible Municipality officer, if not the Mayor himself/herself and someone from the Ministry of Health, if not the Minister of Health himself. Each press conference should have ready for distribution a news release or long feature article with human interest dimensions and photographs, such as the expressed delight of a woman successfully carrying out MNM6/EB6 ,  the case for 6-months rather than 4-months exclusive breast-feeding, the rationale for why no water or additional nutrients are needed during the first six months, a photograph showing the size of an baby’s stomach the first few days with an article on why the baby needs very little to feel full and why mothers should not worry about the baby not getting enough milk, etc. These should be prepared by contracted writers/free lance journalists. Each press conference should provide an opportunity for journalists to ask questions of key technical experts. A simple reception should be held at each press conference.

    - In addition, every month a feature story should be written by a contracted writer/journalist, again with a human interest dimension and reflecting the different aspects of the behavioural theme and rationale (the 21 Things Your Should Know), and made available to the newspapers.

    - Arrangements should be made for three radio talk/chat/discussion shows (one every four months) on the appropriate Beijing  radio network, one hour long, with a panel of two MNM6/EB6  experts (male and female), and a telephone call-in component. The first three questions should be pre-arranged with colleagues to call in to get the discussion going. Similarly, three television calls-in chat/discussion shows should be organised with the Beijing Television system. It would be best if these radio and television shows are existing talk shows dedicated on these three occasions to MNM6/EB6  . Both radio and television shows should be done before a live audience, inviting questions from the audience also. These features (the live audience and call-in) provides for the phenomenon known as “vicarious interaction” which makes people feel they are part of the on-going conversation and this facilitates internalization of the behavioural messages. (Other more popular radio-tv outlets may also be used in a similar fashion depending on availability and costs. If possible, these programmes should also be broadcast via the Village Broadcast Centers.)

    - A short 14-minute video should be produced on the MNM6/EB6 , as  described in 3.31.9.2. This video will be used in the Mothers’ Class as part of prenatal care but should also be used in part at the beginning of the television talk shows and should then lead to discussion and questions from the audience or called-in. It may also be used by the television documentary departments of the various TV channels in Beijing for insertion in other health-related documentary shows.

    - A series of 10 15-second sound bites in scripted form covering ten different aspect of the MNM6/EB6  behavioural message. These are to be used as “fillers” by radio disc jockeys (DJs)/announcers to fill time in between playing musical selections. For e.g., after a tune is played, the DJ says, “Hello to all new mothers…this must be a wonderful moment  in your life. Remember the best welcoming gift for your child after 9 months within you is MNM…mother’s natural milk…for a full six months and nothing more…nothing artificial…no water, no foods, no other liquid…just your loving MNM.” These will be distributed to all radio stations in Beijing (including village broadcasting centers) with a request that they be used during particular periods (to be specified) and used in whatever order but used several times in the day.

  - A Beijing advertising campaign will also be an integral part of the COMBI Plan. This is further detailed later in the plan. It will consist of a minimum of 4 three-week flights of advertising during the course of the first year, done in M-RIP (Massive, Repetitive, Intense, Persistent) style via radio, television and newspapers. The advertising effort is intended to keep on the public agenda the theme of MNM6/EB6  and generate mass reinforcing support for its practice, and to lend support for the door-to-door work of the BLAs.

    - The campaign will consist of  4  three-week spurts (or flights), during the year, with radio advertising consisting of 60-second and 30-second spots played 6-8 times per day for 5 days per week in each flight,  television spots  (60 seconds and 30 seconds) 2-3 times per evening five days per week in each flight and full-page print advertisements during the first week of each flight. Preferably a competent local advertising agency could be used. The advertising should be heavily discounted but they will be paid for to ensure broadcast of the spots at specific times and placement of print ads in pre-selected locations in the newspaper. The Beijing/state broadcasting facility  and village broadcasting centers should be used but other media institutions may also be part of the campaign, if funds allow.

  - Point-of-Service promotion should also form part of this COMBI Programme. This will take four forms:

    - A MNM6/EB6  Flag done up in the colours of the MNM6/EB6  logo and with the new logo should be posted (three at a time) at each of the health facilities where prenatal  and post natal care is given and where baby deliveries take place (approximately 1,500 flags?) The flag is not to be in the standard style of national flags but more in the shape of danglers, 45 cm by 120 cm, with the dangler hanging with the long end in vertical position. The flag becomes a visual reminder of the recommended behaviour to people passing by or coming in.

    - In each of the above health facilities, at the entrance way there should be three large posters prominently  with the MNM6/EB6  message as in 3.28. above.

    - In the nurse’s/midwife’s /doctor’s room for pre- and post- natal care , there should also be the same three posters, as reminders to the to all of the behavioural message. Similarly in the post-delivery room, there should be three of the posters one after the other in a highlighted spot.

    - At all pharmacies and supermarkets or shops where formula milk is sold, arrangements should be made to put up multiple sets of the MNM6/EB6  posters, particularly in close proximity to where the infant formula products are sold.

  - The COMBI Programme will begin with administrative mobilisation (official memoranda/circulars from the Mayor of Beijing/Beijing Health Bureau, and  the Minister of Health) accompanied by staff meetings of senior officers, and associated staff meetings at all levels ) and directed at engaging all 130,000 (check number??) health staff in Beijing at all levels (county, district, township, village, and including the lowest level staff, such as cleaning staff)  in Beijing , to actively participate in this COMBI effort for MNM6/EB6 . The MNM6/EB6  memo should present the case for the new initiative and inviting committed support form all health staff. In addition , Beijing Health Bureau (BHB) will also mobilise the volunteer services of the All Women’s Federation and the Neighbourhood Committees. The Mayor’s Office will launch the COMBI Plan with a Gala Concert of  top-rated Beijing singer to which will be invited all senior officials of the Ministry of Health and staff of the BHB, and the BLAs.

  - A Business Partnership for Baby Love will be created and will comprise representatives of selected business companies in Beijing such as a cell phone company, a bank, supermarket companies, airlines, travel tour companies, and selected companies with products for children but not infant formula companies, and others. These partners will be invited to fund different components of the proposed COMBI Plan (such as providing gifts for the BLAs, and the Lucky Draw Prizes, with discreet acknowledgement given for their contribution.

  - The COMBI Plan will be managed by a team to be called the Implementation Group comprising officers from the Beijing Municipal Health Bureau, the Capital Institute of Pediatrics, the WHO Collaborating Center for Child Health, the China Society for Child Health, Beijing Association of Maternal and Child Health Care, China Advisory Center for Child Health and Disease Control, the All Women Federation,  representatives of  WHO and UNICEF and NGOs working on breast-feeding, representatives of the Beijing radio-tv system; and selected other partners. This group to be called the Implementation Group will be co-chaired by a senior officer from the Beijing Municipal Health Bureau and the CIP. One senior staff  member of the CIP should be designated the chief staff person responsible for coordinating day-to-day execution of the programme and will be called the COMBI Coordinator. He/she will be supported by a new hire to be called the COMBI Manager attached to CIP but working with the COMBI Coordinator. The COMBI Manager will deal with the fine details of implementation. This Implementation Group will meet once per week in the first four months of the programme and afterwards once per month, for coordinating implementation and monitoring implementation progress,

  - Impact Evaluation:

    - Behavioural impact will be measured by tracking the exclusive breast-feeding behaviour of a random sample of mothers who have given birth in the first 9-months from the launch of the COMBI Programme. The survey will track with a sensitively designed questionnaire the breast-feeding practice of these mothers during the first six months of their baby’s life. In this way we will have a measure of those who carried out proper exclusive breast-feeding for whatever duration of time, and why they stopped if they stopped during the six months, and also a measure of those who carried “almost exclusive breast feeding” and for what duration of time. This evaluation/tracking will be carried out by CIP.

    - A mid-project tracking survey (small random samples of about 100 each) in four communities will track exposure to and comprehension of the behavioural theme in the media.

  - It is widely acknowledged in the private sector world of integrated marketing communication, the consumer communication  world, that behavioural responses are possible only with a smart blend of mass media, personal selling/interpersonal communication, promotional triggers and related public relations/advocacy. The COMBI Plan as detailed below may seem an excessive and messy blend. But it follows the recommended style of M-RIP: Massive, Repetitive, Intense, and Persistent. And all of it is necessary. In marketing communication experience, there is the view that to have behavioural impact, an individual needs to be “hit” with the behavioural message about 6 times per day over several days per week over several weeks. The above strategy should lead to a variety of hits per day and during the pre-natal and post natal care of the mother and child. Non-COMBI specialists are likely to be tempted to eliminate several communication interventions if budget crunches appear. It is important that, if there is a budget crunch, decisions on what blend of communication interventions to retain be made by COMBI specialists in close consultation with the Implementation Group. In addition, we should avoid the temptation of carrying out the programme in piece-meal fashion, meaning that we’ll do some personal selling this month, and then sometime later we’ll have a press article and a press conference, and then later in the year we’ll do some advertising, etc. Ideally, this integrated  plan should be synchronised and strategically implemented so that the different pieces providing reinforcing support to each in a timely fashion during the implementation year.

  - Prerequisite Reminder: One emphasises the prerequisite of retraining all relevant health staff  on The MNM6/EB6

4.  Communication Actions

(Note: The actions below make operational the strategic interventions described in Section 3 above. Hence one will note a fair amount of repetition. Each of the actions below will require their own implementation micro plans; in preparing the detailed work plan, under each activity, one should therefore insert a line for developing the micro plans.)

  - New Branding of Exclusive Breasting Feeding Behaviour: MNM6

    - Design a new logo and branding theme for the recommended behaviour.  See guidelines in section 3.28 above. This is to be used on all materials dealing with this COMBI Plan  in Beijing.

    - Develop a micro plan for this activity, perhaps involving a selected local design firm, or running a competition among design/advertising agencies, with a fixed monetary prize for the winner.

  - Administrative Mobilisation

    - Carry out a programme of activities  for Administrative Mobilisation, consisting of staff meetings and consultations, and the widespread, extensive distribution of  and staff discussion at all levels of a MNM6/EB6  briefing memo, and associated memos..

      - Prepare a two-page briefing paper in Memorandum format with the MNM6/EB6  logo signed by the Mayor of Beijing (and the Minister of Health??), possibly with photographs. The memorandum should describe the new thrust in getting higher levels of  exclusive breast-feeding for 6 months and not just 4 months as previously promoted in Beijing and why, and should present the outline of the COMBI Plan to be implemented with its behavioural focus. The memo should begin with an expression of appreciation for the past work done on exclusive breast feeding so far but drawing attention to the remaining challenges, and calling for continued vigorous support of the COMBI initiative focused on the specific desired  behavioural outcome. The briefing memorandum is to be distributed to all staff at all levels in the Beijing health system.

      - Print 130,000 copies of the Briefing memorandum, single page, both sides, with the new logo , on coloured stock with one additional colour, or two colours on white stock.

      - Hold meeting of all senior staff of the Beijing Municipal Health Bureau, chaired by the Mayor and Deputy Mayor responsible for Health including senior staff of the Department of MCH and Community Health, Department of Hospital Administration, District/County MCH Hospitals, District/County Health Bureau, Township Government and Village Health Stations, and CIP .

        - Share briefing paper and further explain COMBI Plan to be implemented, with the new logo and behavioural theme.. This meeting is to secure and confirm commitment at the most senior level of the MOH. Specific mention should be made of the rationale for the new thrust, why six months  of proper exclusive breast-feeding rather than 4, the expected actions of staff during pre-natal care and the Mothers’ Class, and the actions at the time of delivery and within the first hour of birth, including he various Lucky Draws and the use of Gold Star stickers etc.

        - Also to be stressed is the need to have the briefing paper  distributed to every single staff member and to have it discussed as an agenda item at one of the regular supervisory meetings held at the various levels (an including all staff—not just technical staff, but clerical, support, cleaning staff, etc--at every level), with feedback sent on to the Mayor’s office.

        - In addition, attention should be drawn to the separate activity of re-training all technical health staff on exclusive breast-feeding for six months. It should be pointed out that selected technical staff (doctors/nurses) will be need to train the Baby Love Ambassadors as described in the COMBI Plan and to serve as on-going mentors to the BLAs.

      - Issue/distribute an official memorandum with the Briefing Paper  from the Mayor/Deputy Mayor  to each County/District  Health Chief, explaining the new COMBI Plan for MNM6/EB6  and inviting their keen support and involvement and requesting that the Briefing Paper be distributed to every single staff member and be discussed at the next supervisory meeting held by any supervisor for staff at all levels

      - Check that Health Center directors have held in-house meetings as requested.

      - Check that information to all staff at the County/District/Township/Villagelevels have been delivered, through the Briefing memorandum and  through one of the regular meetings of staff.

      - Arrange for the Gala Performance Launching Event to launch the COMBI Programme (See 3.35 above)

      - Develop micro implementation plans for each of the above activities, as appropriate.

  - Public Relations

    - Carry-out a programme of Media-Based Public Relations/Promotional activities  to put on the public agenda the issues surrounding MNM6/EB6  recommended behaviour in Beijing and why Beijing  Health Bureau (BHB) is taking special intensive action, and what specific behaviour is being urged:

      - Contract a freelance writer/journalist.

      - Prepare a two-page press release (written in journalistic style) and based on the briefing memorandum, announcing plans to embark on a COMBI strategy to encourage MNM6/EB6  behaviour for, and explaining why Beijing Health Bureau is taking special intensive action.

      - Hold press conference, and an extended press briefing following the formal press conference to announce the launch of the COMBI Programme and the behavioural objective with its rationale, for the Mayor, Deputy Mayor in charge of Health, and the Minister of Health (??) and senior officials of the Beijing Health Bureau (BHB) and CIP, distribution of a small press kit comprising the press release and background documents  for distribution to the media representatives, including general information on the benefits of proper exclusive breast-feeding for six months.  BHB/CIP technical staff should conduct the press briefing which should follow the press conference and should be about an hour long. Staff should be prepared to respond to queries about the breast-feeding situation and questions regarding the rationale for the specific MNM6/EB6  behaviour being recommended, rather than the former EB4  behaviour.

      - Prepare and distribute to print media in Beijing  a major press release of a 2000-word feature article on MNM6/EB6  based on the briefing document but written in journalistic style and featuring various quotes from BHB/CIP staff (men and women),  and others, including UNICEF, WHO in Beijing. The feature article should be supplemented by photos and should address the key questions that are popularly asked about MNM6/EB6  behaviour, including the items in the 21 Things You Should Know….. The feature should anticipate popular questions to be asked.

      - Prepare and distribute for radio and television a 2-minute press release with sound/video bites from the MOH covering some of the same themes as the feature article/press release above, for use in radio-television news programmes.

      - Prepare every month at least one 1500-word feature article to be offered and hopefully to appear in each of the major Beijing newspapers, covering some aspect of MNM6/EB6    or some aspect of the COMBI Programme, such as the start of the personal selling, or  personal stories and testimonials (with photos) of people carrying out the recommended behaviour and proclaiming how wonderful it feels.

      - Produce and broadcast three one-hour radio discussion programmes with invited telephone call-in on Beijing Radio, once every four months. The show hosted by a good moderator and two articulate MNM6/EB6  specialists (one male, one female) should discuss various issues related to  MNM6/EB6  but with special emphasis on the key behavioural messages. The show should be done in front of a small live audience if possible. The show should try for a blend of music and chat. Some of the telephone calls should be pre-arranged to get the process going.

      - Produce and broadcast three one-hour television discussion shows with telephone call-in on Beijing Television, similar in format to the radio discussion show, once every four months. This show should be done in front of a live audience if possible.

      - Produce a 14-minute video focused on the behavioural theme and rationale (described in 3.31.9.2), and distribute to all television stations. (Also to be used in Mothers’ Classes in the pre-natal services)

      - Arrange to use the 14-minute video as a trigger for discussion on the television chat/call-in show discussed above.

      - Arrange for the behavioural theme to be raised/presented in existing drama shows on radio-TV in Beijing at least once every four months during the year.

      - Prepare ten (10) 15-second sound bites in scripted form covering ten different aspect of the MNM6/EB6  behavioural message. These are to be used as “fillers” by radio disc jockeys (DJs) to fill time in between playing musical selections. See  3.32.5 above.

      - Distribute the pack of 10 “filler” scripts to each radio station with a request that the DJs use them from time during the day (as a public service for child health and development), preferably about 8 times during the day, either repeating the same filler or mixing them. The radio stations should be urged to use these fillers over one two week period to be specified/suggested  in every three months.

      - Re-send the same pack of 10 “fillers” or slightly modified ones just before the specified two week period  in every three months/quarter (with a reminder note and specifying the desired two weeks for the use of the fillers) to all radio stations

  - Personal Selling/Door-to-Door Communication

    - Baby Love Ambassadors (BLAs) Home Visits

      - Prepare and send a memorandum from the BHB Director (or senior official) to all xxxx directors of health centres in Beijing   outlining the exclusive breast feeding situation and challenges, the COMBI Programme ,the new MNM6/EB6  thrust and the   behavioural messages to be promoted, and calling for their keen, passionate involvement. The memo should thank them for the excellent past efforts. The memo should then proceed to spell out the expected roles of health staff in pre-natal, delivery, and post-natal care in the promotion of MNM6/EB6 , and their special role is serving as mentors/informal supervisors of a designated core of volunteers (1,500), selected from the All Women’s Federation who will serve as BLAs, as described in Section 3.31 above.) The memo should direct each health centre director in consultation with the All Women’s Federation and Neighbourhood Committees to  select a certain number of BLAs as per the criteria set out in 3.31 above , and make arrangements for designating their area of coverage and the number of household to likely be visited where there is expected to be women returning home after delivery , as detailed in Section 3.31, for house-to-house sessions. The memo should stress the role of the designated doctors/nurses as Mentors, trainers,  and informal supervisors of the BLAs.

      - Prepare and send a memorandum from the BHB Director (or senior official) to the Director of the All Women’s Federation  and the Neighbourhood Committees presenting the COMBI Plan, its purpose and rationale, and inviting the support and participation of the Federation and Committees in working together with health staff at the various health facilities to identify 1,500 women as per the criteria in 3.31 above who can serve as BLAs.

      - Arrange a meeting between BHB and the Federation and the Neighbourhood Committees to work out details of the process for identifying the BLAs,  training them,  and assigning them to specific areas.

      - Finalise the selection of the 1,500 BLAs.

      - Issue a letter from the Mayor’s office to each BLA congratulating them on their selection and thanking them for being willing to provide this volunteer service for the benefit of children in Beijing, and advising them of the upcoming training for them, the social gatherings and the Thank You event at the end of the year with the Lucky Draw and the prizes and gifts.

      - Design and produce 5,000 pin badges, in the MNM6 logo colours and with the logo, to be given to all BLAs and all health staff involved in pre- and post-natal, and delivery care. The BLAs will wear these badges when visiting homes; and the health staff will also wear them at work.

      - Design and produce 1,500 BLA badges to be worn by the BLAs. They will wear both badges when they visit homes for breast-feeding counselling.

      - Design and produce 1,500 coloured light cotton “waistcoat  vests” (a sort of jacket which one wears over a shirt or dress, like the safety vests some police/traffic officers wear but not necessarily in that expensive fluorescent material), emblazoned with the MNM6/EB6  logo and the “Baby Love Ambassador”  title . These are to be given to the BLAs to wear when they make their home visits.

      - Write, design and print 1 million copies of a MNM6/EB6  Advisory/Information Sheet, A-4 size, two-sided , single sheet, two colours, with content as described in Section 3.31.1 above, with the new logo, with the focus on the behavioural theme and rationale.  These are to be distributed by the BLAs on their home visits. And they are also to be used by health staff at pre-natal visits, including the Mother’s Class.

      - Design and print 5,000 Certificates of Appreciation, to be electronically signed by the Mayor (and Minister of Health?), to be given out to the BLAs at the Thank You ceremony to be held close to the end of the first year.

      - Prepare a 4-page Training Memo to be sent to each Health Centre Director with instructions and guidelines on how to carry out a two-day non-residential training of BLAs with regard to the MNM6/EB6  behaviour and its rationale plus the issues mentioned in 3.31.6 above, with special emphasis on role-playing of the door-to-door-visits by BLAs. (The Health Centre Director and key staff have been involved in sufficient training and so no additional training for them is intended. On the basis of the Training Memo they should be able to carry out a simple training exercise for the BLAs.)

      - Arrange for the BLAs to undergo two one-day non-residential training at each health centre conducted by the midwife and the Health Centre Director.  A lunch and tea/coffee breaks will be served for the BLAs.

      - Arrange for the BLAs at the training to be given the MNM6/EB6  badge, vest, Advisory Sheets, MNM6/EB6  Gold Star Stickers, and small gifts to give to mothers.

      - Arrange for the BLAs to meet with their Health Centre Directors/ key staff members designated their Mentors at each health centre to plan/schedule their home visits in their designated areas, how they will be notified of a mother with a newborn returning to home from the hospital, and  discuss once more exactly what they will do at each home visit to stress the behavioural theme.

      - Arrange for the home visits by the BLAs to begin right after the official launch of the COMBI Plan.

      - Arrange for press coverage of the launch of the BLAs’ work.

      - Arrange for the collection of small gifts from the private sector ia the Business Partnership to be distributed to the BLAs on 4 occasions in the year.

      - Hold a modest community social (simple refreshments) event at the county/district or sub-district level in the first three month of the COMBI Programme under the auspices of  the Mayor’s Office and the county/district medical team. Thank the BLAs for their home visit work and continued support, distribute gifts, and invite them to share their experiences and challenges.

      - Hold another similar community event in the second quarter.

      - Hold a similar event in the third quarter.

      - Arrange to secure 20 airline/hotel package tour prizes  -- for  holidayresort -- donated by the private sector via the Business Partnershipfor BLA/Mentor winners to be given out as part of a lucky draw event at final Thank You Ceremony, described below.

      - Hold a Thank You Ceremony event for the BLAs and Mentors with a simple meal served. At this ceremony, the Mayor thanks each BLA for their work, distributes gifts, and gives each a Certificate of Appreciation. A lucky draw is conducted from among the names of all BLAs present; the lucky winners (the BLA and her Mentor) are given the airline/hotel tour packages as their prizes.

    - Health Staff “Personal Selling” During Pre-Natal, Delivery, and Post-Natal Care.

      - Arrange for a special memo to be sent by the BHB to all appropriate health staff and their supervisor via the Directors of Health, requesting support of the new MNM6/EB6  initiative and thanking them for their considerable efforts in the past, and describing the very specific actions requested of individual staff members as described in 3.32.9 above, and further requesting that each supervisor/Director of Health Centers have a detailed discussion (with role playing as appropriate) with the appropriate staff members about each of the actions so described. The memo should also note that these health staff members coming into contact with a pregnant woman/mother with a newborn should wear the special MNM6/EB6  badge at work.

      - Monitor that supervisors/Director of Health Centers have conducted those discussion sessions with appropriate health staff.

      - Print and distribute to all health facilities providing pre-natal care 150,000 copies of the Information Card #1, Information Card #2; Invitation Card to Mothers’ Class, and  MNM6/EB6  Request Card, all described in 3.32.9 above.

      - Arrange for the collection of the small gifts to be given out at various occasions to mother-to-be as described in 3.32.9.

      - Arrange for the gifts to be collected out in the Lucky Draw of the returned MNM6/EB6  Request Cards (as described in 3.32.9)

      - Establish system for collecting the MNM6/EB6  Request Cards ticked off by a mother after receiving the baby within the first hour and for holding the Lucky Draw of these MNM6/EB6  Request Cards.

      - Arrange for the MNM6/EB6  Advisory sheets, the Request Cards,the Information Cards, the Invitation Card,   MNM6/EB6  badges, and the 14-minute Video (to be used in Mothers’ Classes) to be distributed to all appropriate health staff and the MNM6/EB6 Gold Star stickers for the attending health staff at delivery. (See 3.32.9 for description of use of each of these items.)

      - Arrange for and hold the MNM6/EB6  Request Card Lucky Draw events.

      - Arrange for random monitoring of health centres by BHB and CIP staff to examine the work of the specific staff members mentioned above.

      - Share the report of this monitoring with all appropriate health staff at the various centers in mid COMBI Plan.

      - Arrange for a Thank You memorandum at the end of Year I to be sent to each staff person by the BHB thanking them for their services for MNM6/EB6 , and inviting them to the Thank You Ceremony  being held for the BLAs, with a description of the Lucky Draw to take place.

  - Advertising

    - Plan and execute an M-RIP  (Massive, Repetitive, Intense, Persistent) Radio-TV- Newspaper advertising campaign (to be carried out in collaboration with an “advertising agency” to be contracted by BHB/CIP).

    - Make arrangements for selecting an “advertising agency”, including sending out a creative brief (based on this COMBI Plan) and having invited agencies make short presentations on their creative treatment.

    - Confirm “flight” scheduling of campaign allowing for 4 flights of 3 weeks duration during the course of one year with breaks/pauses between the flights ranging from 2-6 weeks . (The advertising campaign will be carried out in “flights” over the one-year period. A flight is defined as that period of time during which the advertisements take-off or are run (say three weeks), followed by a pause of several weeks (about 2-6 weeks), and then followed by another flight of  another three weeks, another pause, and so on. Strategic and constant repetition is key in advertising.  The ads, reinforcing each other in each medium, will reach key opinion leaders (KOLs)  who in turn further disseminate the messages and stir interpersonal chat. )

    - Confirm agreement on style of advertising. The electronic media advertising should avoid excessive creativity, gimmickry and frivolity (excess of music, dance, cleverness, etc.). We are dealing with serious themes and while some humour/music can be there, the advertising should have the air of an intimate conversation with the listener/mother, husbands, in-laws, grandmothers, an act of engaged communication. Simple, elegant production values are needed. These spots should be earnest, calm, very intimate chats with the audience. On radio and TV one is always communicating with just one other individual. Intimacy is important for the critical subject of  breast feeding and mother-child loving care. The content of all the ads should focus on the behavioural response being sought with precise and intimate explanation of why the behaviour is being recommended.

    - Develop content of the advertisements for radio, television, newspapers with reference to the themes of Section 3.23  above. The advertisements should focus sharply on the behavioural theme, and the rationale for the behaviour. The behavioural theme should be stressed at least three times in each ad.

    - Produce 60-sec and 30-second versions for radio and television advertisements, and full-page and half-page for newspapers. It may be necessary to produce two or three different spots for radio and TV in order to incorporate the key themes listed in Section 3.23 above. Some of the spots should refer to the planned home visits by BLAs.

    - Arrange for placement of ads on radio-television, and newspapers. In the first flight, 60-second radio and television spots should be used for the 3 week flight, five days per week. Radio spots should be scheduled for 8 times per days, and TV spots  three per evening. In the other 3  3-week flights, the schedule should remain the same except that 30-sec spots may  be used on radio-TV. Similarly with newspapers, one can begin with full page ads three times per week in each week of the first flight, reducing to half-page ads three times in the first week of each subsequent flight. Note: BHB/CIP should engage in formal negotiations with the media on advertising costs and should request heavily discounted rates. This could include some free spots in relation to paid spots. The selected advertising agency can advise on best media to use but do note the need to reach the large rural population. Perhaps all the advertising can be provided at no costs for the BHB.)

    - Monitor implementation of radio-television-newspaper advertising and make adjustments depending on public feedback and results of small tracking surveys (described below under “Impact Evaluation”).

  - Point of Service Promotion

    - Produce 1500 MNM6/EB6  Flags/Danglers as described in Section 3.34.1 above and arrange to have these danglers/flags flown at each health facility providing pre-, post-natal, and delivery care.

    - Produce 50,000  MNM6/EB6  posters as described in 3.34 above on the behavioural theme.

    - Arrange to have these posters placed as described in Section 3 at health centres (three, each right next to each other, in the entrance way of the health centres, and three similarly posted  in the pre-natal/post-natal service rooms,  the wards where women with newborns stay after birth, and at supermarkets, small shops and pharmacies.).

    - The Business Partnership for Baby Love

      - Establish a Business Partnership for Baby Love by inviting representatives of selected business corporation as mentioned in Section 3.36 above.

      - Hold first meeting between BHB/CIP and the Partnership.

      - Arrange with the partnership the donation of small gifts to be given out to BLAs four times per year, and small gifts to given out to appropriate health staff at the end-of year Thank You Ceremony.

      - Arrange with the partnership for the Tour Prizes for the Lucky Draw event at the Thank You Ceremony.

5. Impact Evaluation

  - Arrange for behavioural impact evaluation based on an on-going tracking survey as described in 3.38.1 above.

    - Develop micro plan for the above random sample survey of mothers who gave birth in the first 9 months of the COMBI Programme.

  - Conduct mid-project tracking survey in 4 communities  to track exposure and comprehension of messages disseminated via the media and any behavioural trends.  .

6. COMBI Programme Management and Work Plan

  - Management

    - Appoint the Implementation Group (IG) (as described in 3.37 above)

    - Appoint the Co-Chairpersons of the IG

    - Appoint the COMBI Coordinator

    - Recruit the COMBI Manager

    - Schedule and hold meetings of IG.

  - Work Plan

    - The above list of communication and managerial actions in Section 4, 5, 6 will be laid out in a detailed implementation work plan with appropriate scheduling of activities and identification of persons responsible for implementation at all levels. This exercise should be a group exercise involving the many individuals who will be involved in implementation, including the proposed IG.  (The above activities will be repeated below in Annex I as a tentative Work Plan but laid out in landscape format with columns for designating persons responsible and setting time lines.)

OVERVIEW OF China-Beijing Exclusive Breast-Feeding COMBI PLAN

May, 2009 – April, 2010

- Behavioural Objective:

To have 80% (120,000 women) of all women giving birth in Beijing/China during the 12 month period of May 2009 and April 2010 (projected to be 150,000 women giving birth annually) “exclusively breast feed” their baby for a period of six months from within one hour of birth to the end of the first six months, meaning that they  feed the baby nothing else but breast milk, not even water, no other liquids and no other food but breast milk. This behaviour will be referred to as EB6 Behaviour to be re-branded Mother’s Natural Milk exclusively for six-months (MNM6/EB6 )

- COMBI Strategy and Interventions:

SUMMARY OF COMMUNICATION INTERVENTIONS

MNM6/EB6 Behavioural Theme
“Your baby’s first six months: Nothing but the Very Loving Best! Mother’s Natural Milk MNM . And absolutely nothing else! All your baby needs is right there in your loving breast milk for intelligence and miraculous growth for your baby. And  prevents cancer in you

No water, no other liquid, no other food—for the first six months. Just MNM.

- Branding of Behaviour: Develop new logo—suggested MNM6..

- Administrative Mobilisation: Memos to all staff in Beijing Health system, Staff Meetings,  other administrative meetings ,couny/district/township/village  level meetings of  field  health staff—all levels and all staff to be covered.

- Public Relations/Media-Based Promotion:  Gala Launching Event/Press Conference; Feature articles, radio-TV talk/call-in discussion shows, video, other Press Conferences and Press Briefings, and “filler” announcements by DJs on radio; possible insertions in radio-TV dramas.

- “Personal Sellers”: 1,500 volunteers( selected in collaboration with Women’s Federation)  to be branded “Baby Love Ambassadors” (BLAs) will visit every household with a mother and newborn once per week during the first six months of birth, delivering a MNM6/EB6 Advisory sheet.discussing the behaviour, resolving problems, giving out MNM6/EB6 Gold star Stickers for carrying out the behaviour; about ---- health staff engaging warmly and sensitively women coming for pre-natal, post-natal and delivery care engaging mothers-to-be and mothers with newborn about MNM6/EB6, distributing/discussing the Advisory sheet and several small information cards distributed at prenatal visits;  ensuring early attachment within one-hour of birth using a special Request Card  from the mother to the nurse/doctor at time of delivery. Thank You social events  for BLAs and health staff  with Certificates of Appreciation distributed, and Prizes  of tours of resort areas for lucky draw winners at the Thank You ceremonies.

- Advertising: Radio, Television, Newspaper  Advertising— four  3-week flights /year, 8 radio spots per day and 3 TV spots per evening, five days per week in each flight, with full page or half page advertisements three times per week in the first week of each flight.

- Point of Service Promotion: MNM6/EB6 Dangler flags will be posted at all health facilities; MNM6/EB6 posters will be posted in all health facilities, at the entrance way and in doctors’/nurses’ offices as reminders of the behavioural them, and also at pharmacies, supermarkets and small shops selling infant formula.

- The Business Partnership for Baby Love: . A partnership of business representatives will established—for generating small gifts for MCLCAs, prizes for the Lucky Draw, and other co-sponsorship.

- Notes:

  - Carry it out in M-RIP (massive, repetitive, intense and persistent) style.

  - Work for combined effect of multiple interventions – six impressions in short time period for behavioural impact.

  - Management: Implementation Group chaired by Beijing Health Bureau and Capital Pediatrics Institute

  - Budget: One year - US$ 123,200

# Budget				May 2009 – April 2010    		         US $

Note: This is a tentative estimate of costs and will need to be refined. One emphasises: Effective communication for behavioural impact, unfortunately, cannot be done on the cheap. This budget also presumes the usual counter-part contribution of the Beijing Health Bureau in terms of logistics, etc. The budget will be reformulated and so too the COMBI activities when there is a clearer sense of exactly what funds are available and exactly what activities are to be implemented.

### 7.1 New Logo Design				             	 	                         1,000

### 7.2 Administrative Mobilisation

### 7.2.1 130,000 copies of  Briefing Memo                                                              6,000

### 7.2.2  Meetings, travel, refreshments                                                                    3,000

### 7.2.3  Gala Launching Event	                                                                     5,000

Sub-Total:	          14,000

### 7.3Media Promotion

# 7.3.1 Press Conferences/Refreshments	1,000

# 7.3.2 Feature Articles Writing and other press                                                     2,000

# release productions

# 7.3.3 Call-In /Discussion Shows   - Honorarium                             	           1,200

# 7.3.4 Television Call-In/Discussion Shows- Honorarium                                    1,500

# 7.3.5 Writing and distribution of “filler” announcements	1,000

7.3.6 14-min Video						           6,000

Sub-Total:                       12,700

### Personal Sellers: Baby Love Ambassadors (BLAs) and Health Staff

# 7.4.1     5,000 Thank You Certificates	1,000

# 7.4.2     1 million MNM6/EB6  Advisory Sheets                                                  8,000

7.4.3     Thank You Social Event  Costs  	8,000

7.4.4     5,000 MNM6/EB6   and 1,500 BLA plastic pin badges                          4,000

7.4.5     1,500 coloured light cotton vests with logo                                             5,000

7.4.6     Training Guidelines for Mentors of BLAs                                              	    500

7 .4.7     600,000 MNM6/EB6  Gold Star Stickers	 4,000

7.4.8     150,000 MNM6/EB6  Request Cards                                                       2,000

7.4.7     Training Sessions for BLAs: Materials/Meals	 6,000

Sub-Total:                      38,500

# Advertising

7.5.1	Radio-TV-Newspaper Advertising (discounted, co-sponsored)	          20,000

### Point of Service Promotion

    - 50,000 posters                                                                                        7,000

    - 1,500 MNM6/EB6  Flags/Danglers	3,000

Sub-Total:                             10,000

### Evaluation/Research

### Random Sample Tracking Survey of Mothers                                     10,000

### 4  Small Tracking Surveys	3,000

### Sub-Total:                    13,000

### Management

7.8.1 COMBI Manager						         10,000

7.8.2 Administrative Costs	 (beyond counter-part contribution)		           4,000

Sub-Total: 	          14,000

GRAND TOTAL:               $123,200

Annex I: China-Beijing Exclusive Breast Feeding COMBI Work Plan:May 2009 – April 2010

(To be completed in group exercise with implementing staff)

SUMMARY OF COMMUNICATION INTERVENTIONS

MNM6/EB6 Behavioural Theme
“Your baby’s first six months: Nothing but the Very Loving Best! Mother’s Natural Milk MNM . And absolutely nothing else! All your baby needs is right there in your loving breast milk for intelligence and miraculous growth for your baby. And prevents cancer in you

No water, no other liquid, no other food—for the first six months. Just MNM.

- Branding of Behaviour: Develop new logo—suggested MNM6..

- Administrative Mobilisation: Memos to all staff in Beijing Health system, Staff Meetings,  other administrative meetings ,couny/district/township/village  level meetings of  field  health staff—all levels and all staff to be covered.

- Public Relations/Media-Based Promotion:  Gala Launching Event/Press Conference; Feature articles, radio-TV talk/call-in discussion shows, video, other Press Conferences and Press Briefings, and “filler” announcements by DJs on radio; possible insertions in radio-TV dramas.

- “Personal Sellers”: 1,500 volunteers( selected in collaboration with Women’s Federation)  to be branded “Baby Love Ambassadors” (BLAs) will visit every household with a mother and newborn once per week during the first six months of birth, delivering a MNM6/EB6 Advisory sheet, discussing the behaviour, resolving problems, giving out MNM6/EB6 Gold star Stickers for carrying out the behaviour; about 2000 midwives and other health staff engaging warmly and sensitively women coming for their all health staff in pre-natal, post-natal and delivery care engaging mothers-to-be and mothers with newborn about MNM6/EB6, ensuring early attachment within one-hour of birth using a special Request Card  from the mother to the nurse/doctor at time of delivery. Thank You social events  for BLAs and health staff  with Certificates of Appreciation distributed, and Prizes  of tours of resort areas for lucky draw winners at the Thank You ceremonies.

- Advertising: Radio, Television, Newspaper  Advertising— four  3-week flights /year, 8 radio spots per day and 3 TV spots per evening, five days per week in each flight, with full page or half page advertisements three times per week in the first week of each flight.

- Point of Service Promotion: MNM6/EB6 Dangler flags will be posted at all health facilities; MNM6/EB6 posters will be posted in all health facilities, at the entrance way and in doctors’/nurses’ offices as reminders of the behavioural them, and also at pharmacies, supermarkets and small shops selling infant formula.

- The Business Partnership for Baby Love: . A partnership of business representatives will established—for generating small gifts for MCLCAs, prizes for the Lucky Draw, and other co-sponsorship.

.

NOTE: Numerous actions below will require their separate micro-plans and sometimes micro-plans for actions at county/district/townshipt/village level. The activities below should there fore be modified to reflect internal micro-planning steps to be taken.

Activities				         				     				     Completion Date 		              Responsible

  - New Logo/Branding of Exclusive Breasting Feeding Behaviour: MNM6

    - Design a new logo and branding theme for the recommended behaviour.  See guidelines in section 3.28 above. This is to be used on all materials dealing with this COMBI Plan  in Beijing.

    - Develop a micro plan for this activity, perhaps involving a selected local design firm, or running a competition among design/advertising agencies, with a fixed monetary prize for the winner.

  - Administrative Mobilisation

    - Carry out a programme of activities  for Administrative Mobilisation, consisting of staff meetings and consultations, and the widespread, extensive distribution of  and staff discussion at all levels of a MNM6/EB6  briefing memo, and associated memos..

      - Prepare a two-page briefing paper in Memorandum format with the MNM6/EB6  logo signed by the Mayor of Beijing (and the Minister of Health??), possibly with photographs. The memorandum should describe the new thrust in getting higher levels of  exclusive breast-feeding for 6 months and not just 4 months as previously promoted in Beijing and why, and should present the outline of the COMBI Plan to be implemented with its behavioural focus. The memo should begin with an expression of appreciation for the past work done on exclusive breast feeding so far but drawing attention to the remaining challenges, and calling for continued vigorous support of the COMBI initiative focused on the specific desired  behavioural outcome. The briefing memorandum is to be distributed to all staff at all levels in the Beijing health system.

      - Print 130,000 copies of the Briefing memorandum, single page, both sides, with the new logo , on coloured stock with one additional colour, or two colours on white stock.

      - Hold meeting of all senior staff of the Beijing Municipal Health Bureau, chaired by the Mayor and Deputy Mayor responsible for Health including senior staff of the Department of MCH and Community Health, Department of Hospital Administration, District/County MCH Hospitals, District/County Health Bureau, Township Government and Village Health Stations, and CIP .

        - Share briefing paper and further explain COMBI Plan to be implemented, with the new logo and behavioural theme.. This meeting is to secure and confirm commitment at the most senior level of the MOH. Specific mention should be made of the rationale for the new thrust, why six months  of proper exclusive breast-feeding rather than 4, the expected actions of staff during pre-natal care and the Mothers’ Class, and the actions at the time of delivery and within the first hour of birth, including he various Lucky Draws and the use of Gold Star stickers etc.

        - Also to be stressed is the need to have the briefing paper  distributed to every single staff member and to have it discussed as an agenda item at one of the regular supervisory meetings held at the various levels (an including all staff—not just technical staff, but clerical, support, cleaning staff, etc--at every level), with feedback sent on to the Mayor’s office.

        - In addition, attention should be drawn to the separate activity of re-training all technical health staff on exclusive breast-feeding for six months. It should be pointed out that selected technical staff (doctors/nurses) will be need to train the Baby Love Ambassadors as described in the COMBI Plan and to serve as on-going mentors to the BLAs.

      - Issue/distribute an official memorandum with the Briefing Paper  from the Mayor/Deputy Mayor  to each County/District  Health Chief, explaining the new COMBI Plan for MNM6/EB6  and inviting their keen support and involvement and requesting that the Briefing Paper be distributed to every single staff member and be discussed at the next supervisory meeting held by any supervisor for staff at all levels

      - Check that Health Center directors have held in-house meetings as requested.

      - Check that information to all staff at the County/District/Township/Village levels have been delivered, through the Briefing memorandum and  through one of the regular meetings of staff.

      - Arrange for the Gala Performance Launching Event to launch the COMBI Programme (See 3.35 above)

      - Develop micro implementation plans for each of the above activities, as appropriate.

  - Public Relations

    - Carry-out a programme of Media-Based Public Relations/Promotional activities  to put on the public agenda the issues surrounding MNM6/EB6  recommended behaviour in Beijing and why Beijing  Health Bureau (BHB) is taking special intensive action, and what specific behaviour is being urged:

      - Contract a freelance writer/journalist.

      - Prepare a two-page press release (written in journalistic style) and based on the briefing memorandum, announcing plans to embark on a COMBI strategy to encourage MNM6/EB6  behaviour for, and explaining why Beijing Health Bureau is taking special intensive action.

      - Hold press conference, and an extended press briefing following the formal press conference to announce the launch of the COMBI Programme and the behavioural objective with its rationale, for the Mayor, Deputy Mayor in charge of Health, and the Minister of Health (??) and senior officials of the Beijing Health Bureau (BHB) and CIP, distribution of a small press kit comprising the press release and background documents  for distribution to the media representatives, including general information on the benefits of proper exclusive breast-feeding for six months.  BHB/CIP technical staff should conduct the press briefing which should follow the press conference and should be about an hour long. Staff should be prepared to respond to queries about the breast-feeding situation and questions regarding the rationale for the specific MNM6/EB6  behaviour being recommended, rather than the former EB4  behaviour.

      - Prepare and distribute to print media in Beijing  a major press release of a 2000-word feature article on MNM6/EB6  based on the briefing document but written in journalistic style and featuring various quotes from BHB/CIP staff (men and women),  and others, including UNICEF, WHO in Beijing. The feature article should be supplemented by photos and should address the key questions that are popularly asked about MNM6/EB6  behaviour, including the items in the 21 Things You Should Know….. The feature should anticipate popular questions to be asked.

      - Prepare and distribute for radio and television a 2-minute press release with sound/video bites from the MOH covering some of the same themes as the feature article/press release above, for use in radio-television news programmes.

      - Prepare every month at least one 1500-word feature article to be offered and hopefully to appear in each of the major Beijing newspapers, covering some aspect of MNM6/EB6    or some aspect of the COMBI Programme, such as the start of the personal selling, or  personal stories and testimonials (with photos) of people carrying out the recommended behaviour and proclaiming how wonderful it feels.

      - Produce and broadcast three one-hour radio discussion programmes with invited telephone call-in on Beijing Radio, once every four months. The show hosted by a good moderator and two articulate MNM6/EB6  specialists (one male, one female) should discuss various issues related to  MNM6/EB6  but with special emphasis on the key behavioural messages. The show should be done in front of a small live audience if possible. The show should try for a blend of music and chat. Some of the telephone calls should be pre-arranged to get the process going.

      - Produce and broadcast three one-hour television discussion shows with telephone call-in on Beijing Television, similar in format to the radio discussion show, once every four months. This show should be done in front of a live audience if possible.

      - Produce a 14-minute video focused on the behavioural theme and rationale (described in 3.31.9.2), and distribute to all television stations. (Also to be used in Mothers’ Classes in the pre-natal services)

      - Arrange to use the 14-minute video as a trigger for discussion on the television chat/call-in show discussed above.

      - Arrange for the behavioural theme to be raised/presented in existing drama shows on radio-TV in Beijing at least once every four months during the year.

      - Prepare ten (10) 15-second sound bites in scripted form covering ten different aspect of the MNM6/EB6  behavioural message. These are to be used as “fillers” by radio disc jockeys (DJs) to fill time in between playing musical selections. See  3.32.5 above.

      - Distribute the pack of 10 “filler” scripts to each radio station with a request that the DJs use them from time during the day (as a public service for child health and development), preferably about 8 times during the day, either repeating the same filler or mixing them. The radio stations should be urged to use these fillers over one two week period to be specified/suggested  in every three months.

      - Re-send the same pack of 10 “fillers” or slightly modified ones just before the specified two week period  in every three months/quarter (with a reminder note and specifying the desired two weeks for the use of the fillers) to all radio stations

  - Personal Selling/Door-to-Door Communication

    - Baby Love Ambassadors (BLAs) Home Visits

      - Prepare and send a memorandum from the BHB Director (or senior official) to all xxxx directors of health centres in Beijing   outlining the exclusive breast feeding situation and challenges, the COMBI Programme ,the new MNM6/EB6  thrust and the   behavioural messages to be promoted, and calling for their keen, passionate involvement. The memo should thank them for the excellent past efforts. The memo should then proceed to spell out the expected roles of health staff in pre-natal, delivery, and post-natal care in the promotion of MNM6/EB6 , and their special role is serving as mentors/informal supervisors of a designated core of volunteers (1,500), selected from the All Women’s Federation who will serve as BLAs, as described in Section 3.31 above.) The memo should direct each health centre director in consultation with the All Women’s Federation and Neighbourhood Committees to  select a certain number of BLAs as per the criteria set out in 3.31 above , and make arrangements for designating their area of coverage and the number of household to likely be visited where there is expected to be women returning home after delivery , as detailed in Section 3.31, for house-to-house sessions. The memo should stress the role of the designated doctors/nurses as Mentors, trainers,  and informal supervisors of the BLAs.

      - Prepare and send a memorandum from the BHB Director (or senior official) to the Director of the All Women’s Federation  and the Neighbourhood Committees presenting the COMBI Plan, its purpose and rationale, and inviting the support and participation of the Federation and Committees in working together with health staff at the various health facilities to identify 1,500 women as per the criteria in 3.31 above who can serve as BLAs.

      - Arrange a meeting between BHB and the Federation and the Neighbourhood Committees to work out details of the process for identifying the BLAs,  training them,  and assigning them to specific areas.

      - Finalise the selection of the 1,500 BLAs.

      - Issue a letter from the Mayor’s office to each BLA congratulating them on their selection and thanking them for being willing to provide this volunteer service for the benefit of children in Beijing, and advising them of the upcoming training for them, the social gatherings and the Thank You event at the end of the year with the Lucky Draw and the prizes and gifts.

      - Design and produce 5,000 pin badges, in the MNM6 logo colours and with the logo, to be given to all BLAs and all health staff involved in pre- and post-natal, and delivery care. The BLAs will wear these badges when visiting homes; and the health staff will also wear them at work.

      - Design and produce 1,500 BLA badges to be worn by the BLAs. They will wear both badges when they visit homes for breast-feeding counselling.

      - Design and produce 1,500 coloured light cotton “waistcoat  vests” (a sort of jacket which one wears over a shirt or dress, like the safety vests some police/traffic officers wear but not necessarily in that expensive fluorescent material), emblazoned with the MNM6/EB6  logo and the “Baby Love Ambassador”  title . These are to be given to the BLAs to wear when they make their home visits.

      - Write, design and print 1 million copies of a MNM6/EB6  Advisory/Information Sheet, A-4 size, two-sided , single sheet, two colours, with content as described in Section 3.31.1 above, with the new logo, with the focus on the behavioural theme and rationale.  These are to be distributed by the BLAs on their home visits. And they are also to be used by health staff at pre-natal visits, including the Mother’s Class.

      - Design and print 5,000 Certificates of Appreciation, to be electronically signed by the Mayor (and Minister of Health?), to be given out to the BLAs at the Thank You ceremony to be held close to the end of the first year.

      - Prepare a 4-page Training Memo to be sent to each Health Centre Director with instructions and guidelines on how to carry out a two-day non-residential training of BLAs with regard to the MNM6/EB6  behaviour and its rationale plus the issues mentioned in 3.31.6 above, with special emphasis on role-playing of the door-to-door-visits by BLAs. (The Health Centre Director and key staff have been involved in sufficient training and so no additional training for them is intended. On the basis of the Training Memo they should be able to carry out a simple training exercise for the BLAs.)

      - Arrange for the BLAs to undergo two one-day non-residential training at each health centre conducted by the midwife and the Health Centre Director.  A lunch and tea/coffee breaks will be served for the BLAs.

      - Arrange for the BLAs at the training to be given the MNM6/EB6  badge, vest, Advisory Sheets, MNM6/EB6  Gold Star Stickers, and small gifts to give to mothers.

      - Arrange for the BLAs to meet with their Health Centre Directors/ key staff members designated their Mentors at each health centre to plan/schedule their home visits in their designated areas, how they will be notified of a mother with a newborn returning to home from the hospital, and  discuss once more exactly what they will do at each home visit to stress the behavioural theme.

      - Arrange for the home visits by the BLAs to begin right after the official launch of the COMBI Plan.

      - Arrange for press coverage of the launch of the BLAs’ work.

      - Arrange for the collection of small gifts from the private sector ia the Business Partnership to be distributed to the BLAs on 4 occasions in the year.

      - Hold a modest community social (simple refreshments) event at the county/district or sub-district level in the first three month of the COMBI Programme under the auspices of  the Mayor’s Office and the county/district medical team. Thank the BLAs for their home visit work and continued support, distribute gifts, and invite them to share their experiences and challenges.

      - Hold another similar community event in the second quarter.

      - Hold a similar event in the third quarter.

      - Arrange to secure 20 airline/hotel package tour prizes  -- for  holidayresort -- donated by the private sector via the Business Partnershipfor BLA/Mentor winners to be given out as part of a lucky draw event at final Thank You Ceremony, described below.

      - Hold a Thank You Ceremony event for the BLAs and Mentors with a simple meal served. At this ceremony, the Mayor thanks each BLA for their work, distributes gifts, and gives each a Certificate of Appreciation. A lucky draw is conducted from among the names of all BLAs present; the lucky winners (the BLA and her Mentor) are given the airline/hotel tour packages as their prizes.

    - Health Staff “Personal Selling” During Pre-Natal, Delivery, and Post-Natal Care.

      - Arrange for a special memo to be sent by the BHB to all appropriate health staff and their supervisor via the Directors of Health, requesting support of the new MNM6/EB6  initiative and thanking them for their considerable efforts in the past, and describing the very specific actions requested of individual staff members as described in 3.32.9 above, and further requesting that each supervisor/Director of Health Centers have a detailed discussion (with role playing as appropriate) with the appropriate staff members about each of the actions so described. The memo should also note that these health staff members coming into contact with a pregnant woman/mother with a newborn should wear the special MNM6/EB6  badge at work.

      - Monitor that supervisors/Director of Health Centers have conducted those discussion sessions with appropriate health staff.

      - Print and distribute to all health facilities providing pre-natal care 150,000 copies of the Information Card #1, Information Card #2; Invitation Card to Mothers’ Class, and  MNM6/EB6  Request Card, all described in 3.32.9 above.

      - Arrange for the collection of the small gifts to be given out at various occasions to mother-to-be as described in 3.32.9.

      - Arrange for the gifts to be collected out in the Lucky Draw of the returned MNM6/EB6  Request Cards (as described in 3.32.9)

      - Establish system for collecting the MNM6/EB6  Request Cards ticked off by a mother after receiving the baby within the first hour and for holding the Lucky Draw of these MNM6/EB6  Request Cards.

      - Arrange for the MNM6/EB6  Advisory sheets, the Request Cards,the Information Cards, the Invitation Card,   MNM6/EB6  badges, and the 14-minute Video (to be used in Mothers’ Classes) to be distributed to all appropriate health staff and the MNM6/EB6 Gold Star stickers for the attending health staff at delivery. (See 3.32.9 for description of use of each of these items.)

      - Arrange for and hold the MNM6/EB6  Request Card Lucky Draw events.

      - Arrange for random monitoring of health centres by BHB and CIP staff to examine the work of the specific staff members mentioned above.

      - Share the report of this monitoring with all appropriate health staff at the various centers in mid COMBI Plan.

      - Arrange for a Thank You memorandum at the end of Year I to be sent to each staff person by the BHB thanking them for their services for MNM6/EB6 , and inviting them to the Thank You Ceremony  being held for the BLAs, with a description of the Lucky Draw to take place.

  - Advertising

    - Plan and execute an M-RIP  (Massive, Repetitive, Intense, Persistent) Radio-TV- Newspaper advertising campaign (to be carried out in collaboration with an “advertising agency” to be contracted by BHB/CIP).

    - Make arrangements for selecting an “advertising agency”, including sending out a creative brief (based on this COMBI Plan) and having invited agencies make short presentations on their creative treatment.

    - Confirm “flight” scheduling of campaign allowing for 4 flights of 3 weeks duration during the course of one year with breaks/pauses between the flights ranging from 2-6 weeks . (The advertising campaign will be carried out in “flights” over the one-year period. A flight is defined as that period of time during which the advertisements take-off or are run (say three weeks), followed by a pause of several weeks (about 2-6 weeks), and then followed by another flight of  another three weeks, another pause, and so on. Strategic and constant repetition is key in advertising.  The ads, reinforcing each other in each medium, will reach key opinion leaders (KOLs)  who in turn further disseminate the messages and stir interpersonal chat. )

    - Confirm agreement on style of advertising. The electronic media advertising should avoid excessive creativity, gimmickry and frivolity (excess of music, dance, cleverness, etc.). We are dealing with serious themes and while some humour/music can be there, the advertising should have the air of an intimate conversation with the listener/mother, husbands, in-laws, grandmothers, an act of engaged communication. Simple, elegant production values are needed. These spots should be earnest, calm, very intimate chats with the audience. On radio and TV one is always communicating with just one other individual. Intimacy is important for the critical subject of  breast feeding and mother-child loving care. The content of all the ads should focus on the behavioural response being sought with precise and intimate explanation of why the behaviour is being recommended.

    - Develop content of the advertisements for radio, television, newspapers with reference to the themes of Section 3.23  above. The advertisements should focus sharply on the behavioural theme, and the rationale for the behaviour. The behavioural theme should be stressed at least three times in each ad.

    - Produce 60-sec and 30-second versions for radio and television advertisements, and full-page and half-page for newspapers. It may be necessary to produce two or three different spots for radio and TV in order to incorporate the key themes listed in Section 3.23 above. Some of the spots should refer to the planned home visits by BLAs.

    - Arrange for placement of ads on radio-television, and newspapers. In the first flight, 60-second radio and television spots should be used for the 3 week flight, five days per week. Radio spots should be scheduled for 8 times per days, and TV spots  three per evening. In the other 3  3-week flights, the schedule should remain the same except that 30-sec spots may  be used on radio-TV. Similarly with newspapers, one can begin with full page ads three times per week in each week of the first flight, reducing to half-page ads three times in the first week of each subsequent flight. Note: BHB/CIP should engage in formal negotiations with the media on advertising costs and should request heavily discounted rates. This could include some free spots in relation to paid spots. The selected advertising agency can advise on best media to use but do note the need to reach the large rural population. Perhaps all the advertising can be provided at no costs for the BHB.)

    - Monitor implementation of radio-television-newspaper advertising and make adjustments depending on public feedback and results of small tracking surveys (described below under “Impact Evaluation”).

  - Point of Service Promotion

    - Produce 1500 MNM6/EB6  Flags/Danglers as described in Section 3.34.1 above and arrange to have these danglers/flags flown at each health facility providing pre-, post-natal, and delivery care.

    - Produce 50,000  MNM6/EB6  posters as described in 3.34 above on the behavioural theme.

    - Arrange to have these posters placed as described in Section 3 at health centres (three, each right next to each other, in the entrance way of the health centres, and three similarly posted  in the pre-natal/post-natal service rooms,  the wards where women with newborns stay after birth, and at supermarkets, small shops and pharmacies.).

  - The Business Partnership for Baby Love

      - Establish a Business Partnership for Baby Love by inviting representatives of selected business corporation as mentioned in Section 3.36 above.

      - Hold first meeting between BHB/CIP and the Partnerhsip.

      - Arrange with the partnership the donation of small gifts to be given out to BLAs four times per year, and small gifts to given out to appropriate health staff at the end-of year Thank You Ceremony.

      - Arrange with the partnership for the Tour Prizes for the Lucky Draw event at the Thank You Ceremony.

  - Impact Evaluation

    - Arrange for behavioural impact evaluation based on an on-going tracking survey as described in 3.38.1 above.

    - Develop micro plan for the above random sample survey of mothers who gave birth in the first 9 months of the COMBI Programme.

    - Conduct mid-project tracking survey in 4 communities to track exposure and comprehension of messages disseminated via the media and any behavioural trends.

  - COMBI Programme Management

    - Appoint the Implementation Group (IG) (as described in 3.37 above)

    - Appoint the Co-Chairpersons of the IG

    - Appoint the COMBI Coordinator

    - Recruit the COMBI Manager

    - Schedule and hold meetings of IG.

***